File No. 19-75

(ITEM          )  From the Chief Judge, First Judicial District, requesting authorization for a no cost extension of Amendment 1of JusticePoint’s 2018 Pretrial Service contract pertaining to the validation of the Public Safety Assessment.

A RESOLUTION

WHEREAS, The Milwaukee County Board of Supervisors adopted the 2018 budget on November 6, 2017, File No. 17-674, which included contracting with JusticePoint, Inc. for pretrial services for January 1, 2018 to December 31, 2018; and

WHEREAS, On March 22, 2018 The Milwaukee County Board of Supervisors approved amending the contract to include $60,000 of 2017 encumbered funds to conduct a validation of the Public Safety Assessment, File No. 18-215; and

WHEREAS, The Milwaukee County Board of Supervisors adopted the 2019 budget on November 5, 2018, File No. 18-764, which included contracting with JusticePoint, Inc. for pretrial services for January 1, 2019 to December 31, 2019; and

WHEREAS, On June 1, 2016 pretrial services implemented the Laura and John Arnold Foundation’s Public Safety Assessment (PSA) to provide pretrial release recommendations to the Court; and

WHEREAS, JusticePoint, Inc. will contracted with Luminosity, Inc. to complete stakeholder feedback sessions and a validation report pertaining to the implementation of the PSA; and

WHEREAS, As of December 2018 there was $36,021 remaining for the project, as work has taken longer than expected due to data needs; and

WHEREAS, The validation will be completed by the end of June 2019; therefore

BE IT RESOLVED, that the Milwaukee County Board of Supervisors does hereby authorize the Chief Judge to issue a no cost extension with JusticePoint through June 2019 for the validation work to be completed and expend all of the $60,000 encumbered funds for the project.