COUNTY OF MILWAUKEE

INTEROFFICE COMMUNICATION

DATE:		January 11, 2016

TO:	Supervisor Theodore Lipscomb, Chairman, County Board of Supervisors

FROM:	James Tarantino, Economic Development Director, Department of Administrative Services

SUBJECT:	Park East Block 26 – Phase 3

REQUEST

Authorization to enter into an Amended and Restated Development Agreement and an Agreement to Implement Development of Phase 3 with respect to the development of Park East Block 26, East of the Milwaukee River to permit the Developer of Phases 1 and 2 (Park East Two, LLC) to take over the development of Phase 3 from the Original Developer (Park East Square, LLC).

BACKGROUND

Pursuant to CB Resolution 12-474, Park East Two, LLC (“New Developer”) took over the development of Phases 1 and 2 of Park East Block 26 from Park East Square, LLC (“Original Developer”) in August of 2012.  The transaction was memorialized with several agreements: namely, a Development Agreement for Phases 1 and 2 (“2012 Development Agreement”), and Agreement to Implement the Development Agreement for Phases 1 and 2 (“2012 Agreement to Implement”).  At the time, the right to develop Phase 3 of Block 26 was retained by the Original Developer, subject to the original development agreement dated December 21, 2007 and amended six times thereafter, most recently on October 25, 2011 (“Original Agreement”).  Original Developer now desires that Phase 3 be taken over by New Developer.  Because Original Developer retains the right to develop Phase 3, an amendment to the 2012 Development Agreement is necessary to incorporate Phase 3 therein, as is an Agreement to Implement Phase 3.  Because these agreements pre-date changes to Wis. Stat. 59.17(2)(b)(3), they must be approved by the County Board.

To date, New Developer has completed Phase 1 of Block 26, which includes 104 market rate apartments and 7,045 square feet of retail space and parking.  New Developer plans to develop Phase 2 and Phase 3 sequentially, financing the phases together.  Phase 2 will add 82 units along N. Milwaukee Street, including a mix of studios, one-bedroooms, two-bedrooms and townhomes.  The final phase, Phase 3, will consist of 64 units and an additional 4,700 square feet of retail space fronting Ogden Avenue.  In total, 298 parking spaces will serve the apartments and retail spaces on the Property.

The 2012 Development Agreement governs Phases 1 and 2 of Block 26.  Because only Phase 1 is complete, County proposes an Amended and Restated Development Agreement to incorporate Phase 3 therein.  For financing reasons, the project commencement, excavation completion and project completion dates for Phase 2 have been pushed back two months.   Phase 3 is set to follow beginning in 2017.  The full schedule is as follows:

PHASE 2

Project Commencement Date: 			09/01/2016

- Commencement of Excavation

Excavation Completion Date: 			11/01/2016

- Completion of Excavation and

Commencement of Construction

Project Completion Date:				03/01/2018

- Completion of Construction

Total: 18 months

PHASE 3

Project Commencement Date: 			01/01/2017

- Commencement of Excavation

Excavation Completion Date: 			03/01/2017

- Completion of Excavation and

Commencement of Construction

Project Completion Date:				07/01/2018

- Completion of Construction

Total: 18 months

As the 2012 Agreement to Implement only applies to Phase 1 and Phase 2, a separate Agreement to Implement must be put into place for Phase 3.  The Agreement to Implement Development of Phase 3 serves to clarify both the timing of ownership transfer from Original Developer to New Developer and what development agreement governs what portion of the project at each point in time.

Renderings of Phase 3 are attached hereto, as are copies of both the Amended and Restated Development Agreement and the Agreement to Implement Development of Phase 3.

RECOMMENDATION

The Department of Administrative Services – Economic Development Division respectfully requests authorization to execute an Amended and Restated Development Agreement and an Agreement to Implement Development of Phase 3 as it relates to the continued development of Park East Block 26.

_____________________________

James Tarantino, Economic Development Director

Department of Administrative Services

cc: 	Chris Abele, County Executive

Economic and Community Development Committee Members

Kelly Bablitch, Chief of Staff, County Board of Supervisors

Raisa Koltun, Chief of Staff, County Executive’s Office

Katarina Lucas, Research & Policy Analyst

Shanin Brown, Committee Coordinator

Teig Whaley-Smith, Director, Department of Administrative Services