COUNTY OF MILWAUKEE

INTER-OFFICE COMMUNICATION

DATE	:	August 26, 2011

TO	:	Supervisor Lynne, De Bruin, Chairperson

Committee on Economic and Community Development

FROM	:	Craig C. Dillmann, Manager of Real Estate Services

Department of Transportation and Public Works

SUBJECT	:	From RSC & Associates requesting an amendment to the Development Agreement for the 2.13-acre Block 26 (aka Block One) in the Park East Corridor, located between North Jefferson, North Milwaukee and East Lyon Streets and East Ogden Avenue in the City of Milwaukee, east of the Milwaukee River.

POLICY ISSUE:

Revision of the Development Agreement for Block 26 requires County Board approval.

BACKGROUND:

RSC & Associates (“RSC”) closed on the purchase of Block 26 in December 2007 and the County was paid the $2,725,000 purchase price.  RSC was prepared to break ground on the Park East Square project (“Project”) when the economic downturn resulted in the Project lender rescinding RSC’s loan commitment.  Therefore, the construction timeline in the Development Agreement cannot be met until RSC secures replacement financing.

As outlined in the attached letter from RSC, dated August 24, 2011, RSC notes they have worked diligently to modify their project form and function and pursued a variety of financing alternatives needed to fund their Park East Square Project during a challenging financial and economic climate.

RSC has indicated they have expanded their project team to include a Milwaukee real estate development firm, with the strength and experience to assist moving Phase I of Park East Square Project forward.  The new Project mix for Phase I includes 85 apartment units, comprising 20% affordable units, 14,600 square feet of retail and 246 parking spaces, with a development cost of approximately $20 million.

With bank financing being more viable for apartment construction, the expanded Project team is aggressively pursuing conventional bank financing as well as other various funding alternatives to generate the needed Project capital.

The Project architect has furnished the City of Milwaukee with initial design modifications for the new Project mix and will continue to work closely with the City to achieve approval of Phase I.

RSC recognizes they must ultimately return to the County to obtain the approval of an amended Development Agreement incorporating the expanded Project team and the modified Project mix.  Therefore, in order to ensure the necessary time to pursue the County approval, finalize Project financing and advance the modified Project design to City approval, RSC is requesting a nine (9)month extension to the Project Excavation Commencement Date, until June 30, 2012 and sixty days thereafter for the Excavation Completion Date as called for in the Development Agreement.  The nine month extension will also permit commencement of construction during more suitable weather conditions.

An extension will require an amendment to the Development Agreement (“Sixth Amendment”).  The following summary terms and conditions of a Sixth Amendment to the Development Agreement are:

- The Project Excavation Commencement Date, as defined in the original Development Agreement with Milwaukee County, be extended from September 30, 2011 to June 30, 2012 and 60 days thereafter for the Excavation Completion Date.

- In addition to the of $2,725,00 purchase price paid to the County at closing, RSC has subsequently forfeited to the County the entire $50,000 in the Letter of Credit for not meeting the previous Excavation Completion Dates.  The Letter of Credit will be refunded by RSC to the original $50,000 prior to the Excavation Commencement Date.

- In the event RSC fails to achieve the June 30, 2012 Excavation Commencement Date and the Excavation Completion Date 60-days thereafter, the County shall be entitled to all the remedies, rights, terms and conditions accruing in the Development Agreement, including without limitation, a $2,000/day penalty and the County’s option to repurchase Block 26 at 85% of what the County was paid.

- Except as noted above, the terms and conditions of the Sixth Amendment to the Development Agreement of Block 26 would be substantially the same as the terms and conditions of the original Development Agreement.

RECOMMENDATION:

With the strength of the expanded Park East Square development team, the commencement of the Project is greatly enhanced.  The commencement of the Project will lead to increased jobs, tax base and catalyze further development in and in proximity to the Park East Corridor.  Therefore, staff respectfully requests approval of the above-described Sixth Amendment to the Development Agreement for Block 26.

# FISCAL NOTE:

Extending the Excavation Commencement Date for Block 26 until June 30, 2012 and sixty days thereafter for the Excavation Completion Date, pursuant to the Sixth Amendment, will not include the payment of an extension fee.

___________________________

Craig C. Dillmann, Manager

Real Estate Services

Meeting Date:	September 19, 2011

Attachment

cc:	Chris Abele, County Executive

Lee Holloway, County Board Chairman

Jack Takerian, Director, Transportation and Public Works

Brian Taffora, Director, Economic Development

Vince Masterson, Fiscal Mgmt. Analyst-DAS

Blk26DevAgAmnd6