File No. 23-1065

From the Milwaukee County Zoo requesting $450,173 from Agency 194-1945 Appropriation for Contingencies (2023 Fiscal Year) and $1,042,556 from Agency 194-1945 Appropriation for Contingencies (2024 Fiscal Year) to allocate additional funds for Capital Project WZ018501 Humboldt Penguin Exhibit Renovation by recommending the following:

A RESOLUTION

WHEREAS, File No. 22-335 authorized the Executive Zoo Director to accept the State of Wisconsin De Department of Administration Tourism Capital Grant in the amount of $3.5 million to renovate the Humboldt Penguin Exhibit (Penguin Project); and

WHEREAS, design for the Penguin Project began on February 02, 2023 using a Construction Manager at Risk delivery method and the strategy developed was to competitively engage one Contraction Manager for the Penguin Project and Adventure Africa Phase 3 - Rhino (Rhino Project), to overlap construction to minimize cost burden of General Requirements and General Conditions to Milwaukee County; and

WHEREAS, in anticipation of increased costs for the Penguin Project, File No 23-942 approved a $250,000 fund transfer from Zoo funds to the Penguin Project for a total project cost of $3,750,000 and the fund transfer was submitted prior to knowing the cost of construction bids but was done to keep the Project on track; and

WHEREAS, after preliminary review of the construction bids, the cost for the Penguin Project is $5,242,729, which is $1,492,729 over the revised budget of $3,750,000; and

WHEREAS, the cost overages can be explained by two contributing factors. Critical design errors caught in the late-stage design phase and unfavorable market conditions in specialized trade divisions; and

WHEREAS, The Penguin Project will be delayed if the stated additional funding is not approved in the January 2024 County Board cycle. These delays have the following negative outcomes:

- Jeopardy of the State of Wisconsin Department of Administration Tourism Capital Grant Funds - The Project will be at risk of being completed within the allocated Performance Period. The estimated amount of $420,000 would have to be refunded to the Grant Program.

- Additional cost burden of General Requirements and General Conditions - The Penguin and Rhino Projects would not fully overlap. The estimated increase in General Requirements and General Conditions to the Penguin Project budget is $495,000.

- Additional cost of temporary winter conditions - The start of Construction would be delayed. The result would require the Penguin Project to allocate additional funding for temporary winter conditions to ensure proper curing of concrete. This adds additional risk. The estimated increase in temporary winter conditions is $255,000.

- Additional escalation costs of re-bidding - Due to the Milwaukee County Board calendar, the next potential Board Action is March 2024. If additional funding was authorized then, the Penguin Project could be required to rebid, as current bids are valid for 60 days. The projection of escalation would be 3.33% of Construction Costs. The estimated increase in escalation is $145,000; now, therefore,

BE IT RESOLVED, the Milwaukee County Board of Supervisors hereby authorizes and directs the Office of the Comptroller and the Office of Strategy, Budget, and Performance to process an administrative transfer of $450,173 from Agency 194-1945 Appropriation for Contingencies (2023 Fiscal Year) and an administrative transfer of $1,042,556 from Agency 194-1945 Appropriation for Contingencies (2024 Fiscal Year) to Capital Project WZ018501 – Humboldt Penguin Exhibit Renovation.