COUNTY OF MILWAUKEE

INTEROFFICE COMMUNICATION

DATE:	March 17, 2015

TO:		Supervisor Marina Dimitrijevic, Chair, County Board of Supervisors

FROM:	Brian Dranzik, Director, Department of Transportation

SUBJECT:	AMENDMENT NO.  4 TO PROFESSIONAL SERVICE CONTRACT BETWEEN MILWAUKEE COUNTY AND CORLETT, SKAER & DEVOTO ARCHITECTS, INC. (CSDA)

POLICY

A contract amendment, which renders the total contract value greater than $300,000, requires full County Board approval.

BACKGROUND

Implementation of the FAA-approved FAR Part 150 Noise Study Update recommendations required hiring a consultant to manage and implement the Airport Area Noise Management Program (NMP).  The NMP is the result of recommendations made in the Federal Aviation Regulation Part 150 Noise Compatibility Program approved by the FAA in June 2009. The program consists of providing all of the consulting and management services necessary to implement the land and noise mitigation programs of the Noise Compatibility Program (NCP) including the modification of approximately 600 residences to reduce the impacts of aircraft-generated noise on the occupants, sales assistance and avigation easements. The program uses the single parcel contracting method with all construction work performed by local contractors.

CSDA is a full-service architectural firm specializing in the design and implementation of airport sound mitigation programs.  The CSDA consultant team consists of:

- KPH Construction, a Milwaukee-based firm with six years of experience on the previous Milwaukee program.

- Hill International, a national construction management firm with extensive expertise in program documentation management.

- PSOMAS, a national engineering consultant firm with expertise in mapping, Geographic Informational Systems and construction management.

- Geiger Engineering, a Milwaukee-based electrical engineering firm.

- Engineering Concepts, a Waukesha-based full-service engineering firm that will address mechanical engineering design services.

- Toki & Associates, a Wisconsin-based MBE/DBE/SBE firm specializing in architectural and engineering services.

- 2-Story Creative (formerly Weiss, & Company), a Milwaukee-based DBE public relations and community outreach agency.

In a September 24, 2009, Resolution, the County Board approved of retaining CSDA as the program management consultant for implementation of the Noise Management Program.  A professional services contract was executed on March 11, 2010, between Milwaukee County and CSDA for a term of 24 months with a not-to-exceed value of $9,034,427.70.

On March 31, 2010, the County authorized CSDA to proceed with program set-up and residential sound insulation tasks identified in the NMP Scope of Work.

Amendment No. 1 of the contract between Milwaukee County and CSDA was executed on April 2, 2012, for a term of twelve months (April 1, 2012 to March 31, 2013) with a not to exceed value of $5,640,400  to continue implementation of the NMP.

Amendment No. 2 of the contract was executed on March 18, 2013, for a term of twelve months (April 1, 2013 to March 31, 2014) with a not to exceed value of $5,920,000 to continue implementation of the NMP.

Amendment No. 3 of the contract was executed on March 31, 2014, for a term of twelve months (April 1, 2014 to March 31, 2015) with a not to exceed value of $5,256,316 to continue implementation of the NMP. CSDA, during Amendment No. 3, will complete oversight of the last group of 17 single-family homes within the FAA determined eligibility boundary and has started treatment of the 108 multi-family units.

CSDA, during Amendment No. 4, will provide all of the administration and program management services necessary to complete the residential sound insulation program including:

- Sound insulation of 108 multi-family units and remaining eligible single family parcels

- Coordinate and resolve homeowner product warranty issues

- Update and transfer land use GIS mapping to reflect acquisition of Avigation Easements and treatment of more than 650 parcels

- Close the program office and product showroom

- Transfer the electronic program management system and associated database to the airport

- Assist the Airport in FAA program reporting and FAA grant reporting to close the NMP

Federal, State and local funding is currently available to complete the NMP including CSDA Amendment No. 4 upon approval.

DBE Utilization

DBE participation for the small construction contractors performing the home modifications has been 56% to date.  CSDA has committed to continue the 17% DBE goal for professional services on the project including the utilization of Toki & Associates and 2-Story Creative (formerly Weiss & Company).

RECOMMENDATION

The NMP requires the delivery of ongoing professional services by CSDA to complete implementation of the County’s Noise Management Program and close the program in accordance with Federal Aviation Administration requirements.

Amendment No. 4 of the contract between Milwaukee County and CSDA, if approved, shall have a term of four months (April 1, 2015 to July 31, 2015) and a not to exceed value of $1,654,960 to complete implementation of the NMP and close the program.  The FAA requires that the program be closed out by September 30, 2015.

It is requested that the County Board authorize the Director of Transportation and the Department of Transportation-Airport Division to amend its March 31, 2010, contract with Corlett, Skaer & Devoto Architects, Inc., adding $1,654,960 for a term of 4 months (April 1, 2015 to July 31, 2015) to complete implementation of Milwaukee County’s Airport Area Noise Management Program.

FISCAL NOTE

The GMIA Noise Management Program is fully funded in Capital Project WA064.  FAA approval of the individual study elements makes the Airport eligible for Federal funding.  Subject to FAA authorization and appropriations, noise projects are eligible for 80% Federal funding and 10% State funding, with the Airport providing a 10% local funding share through its Passenger Facility Charge (PFC) program.  Amendment of the contract will have no fiscal effect on the tax levy of Milwaukee County.

Prepared by:	Kim M. Berry, A.A.E., Noise Program Manager

Approved by:

____________________				____________________

Brian Dranzik						Terrence G. Slaybaugh

Director, Department of Transportation		Airport Director

Cc:	Chris Abele, County Executive

Raisa Koltun, Chief of Staff, County Executive’s Office

Kelly Bablitch, Chief of Staff, County Board of Supervisors

James Martin, Director of Administration, MCDOT