| Task | Description | Completion Date | Timeframe | Responsible Person(s) |
| --- | --- | --- | --- | --- |
| 1 | Project Team members present the proposed path forward using an incremental decision-making approach to the Parks and/or Finance Committees, depending on the Chairwoman’s referrals (submit report in early or mid-August) | September 14, 2021 (Parks) | --- | Project Team Dept. Leaders (support) |
| 2 | Select financial and legal services vendors to perform independent reviews for discrete components of the Domes project including the funding stack and partnership structure, respectively (contracts will be under $50,000; no RFP is required). Contracts will include required meetings with project team members and/or technical experts within Milwaukee County. | September 14-November 30, 2021 | Ten weeks | Review Team Dept. Leaders (support) Procurement (support) |
| 3 | Project Team members provide an update to the Parks Committee (submit report by November 5) | December 7, 2021 | --- | Project Team Dept. Leaders (support) |
| 4 | Contracts completed for the financial and legal services vendors; work begins | November 30-December 31, 2021 | Four weeks | Respective Department Staff Procurement (support) |
| 5 | Financial and legal services vendors perform analyses and submit preliminary reports to Milwaukee County (meetings with Milwaukee County staff to occur throughout the development of the reports) | January 1-February 28, 2022 | Eight weeks | Review Team Respective Department Staff Project Team |
| 6 | Project Team members provide an update to the Parks Committee | March 15, 2022 | --- | Project Team Dept. Leaders (support) Vendors (as requested) |
| 7 | Financial and legal services vendors perform analyses and submit final reports to Milwaukee County (meetings with Milwaukee County staff to occur throughout the development of the reports) | January 1-April 15, 2022 | Fourteen weeks | Review Team Respective Department Staff Project Team |
| 8 | Department staff and Project Team review final vendor reports and present findings to Dept. Leaders and Administration | May 1-15, 2022 | Two weeks | Review Team Respective Department Staff Project Team |
| 9 | Project Team members provide an update to the Parks (and possibly Finance) Committee | June 2022 (Date TBA) | --- | Project Team Dept. Leaders (support) Vendors (as requested) |
| 10 | Anticipated conclusion of the Safety Mesh Inspection and Repairs Project | June 30, 2022 | --- | Facilities Management Division Vendors |
| 11 | Anticipated conclusion of the Glazing System Renovation Investigation* and updated repair cost estimates upon receiving the consultant’s report. *Significant (8-10 month) delay related to the supply chain beyond Milwaukee County’s control. | November 30, 2022 | --- | Facilities Management Division Vendors |
| 12 | Project Team members provide an update to the Parks (and possibly Finance) Committee | December 2022 (Date TBA) | --- | Project Team Dept. Leaders (support) Vendors (as requested) |
| 13 | ***Pending results of the Glazing System Renovation Investigation and Board direction*** Engage with County residents to discuss the path forward and process through a series of in-person and virtual meetings in conjunction with the Board of Supervisors | January 1-February 28, 2023 | Eight weeks | Project Team Dept. Leaders Administration Supervisors |
| 14 | Project Team finalizes community engagement findings | March 1-30, 2023 | Four weeks | Project Team |
| 15 | Project Team presents updated recommendations to Dept. Leaders and Administration for review and approval | April 1-30, 2023 | Four weeks | Project Team Dept. Leaders Administration |
| 16 | Project Team members report final recommendations on the path forward for the Domes to the Parks (and possibly Finance) Committee | May 2023 | --- | Project Team Dept. Leaders/Administration |
| 17 | Board approval of path forward for the Domes | July 2023 | --- | Board of Supervisors |
| Design and capital project timeline to be determined based on Board-Administration incremental decision-making process. |

KEY

Project Team Items

Facilities Management Division Items

Committee and Board of Supervisors Items