April 28, 2015

Mr. Erik Viel

Director, Radio Services

Milwaukee County Office of Emergency Management

Milwaukee County Courthouse, Room 308

901 N 9th St, Milwaukee, WI 53233

RE: Project Scope and Quotation for Milwaukee County OASIS Public Safety Radio System (Project WO614) Project Management Services

Director Viel,

As the individual authorized to contractually obligate and negotiate for CDX Wireless, I am pleased to present this project scope and quotation for project management services for the OASIS Public Safety Radio System (Project WO614).

If you have any questions please feel free to contact me through the contact information listed below.

Respectfully,

Steve Surwillo

Principal, CDX Wireless Inc.

1434 Spruce Street, Suite 100

Boulder, Colorado 80302

Phone: (847) 774-7102

Fax: (928) 752-0954

Email: steve.surwillo@cdxwireless.com

# Table of Contents

1	Project Staffing	3

2	Place of Performance	3

3	Scope of Work	3

3.1	Background	3

3.2	Work Activities	4

3.3	Schedule of Work	17

4	Price Quotation	18

4.1	Quotation Basis	18

4.2	Work Breakdown and Labor Quotation	18

4.3	Travel and Other Expenses	19

4.4	Invoicing	20

# Project Staffing

CDX Wireless shall staff our efforts on this project with Mr. Steve Surwillo.  Mr. Surwillo has served Milwaukee County on this project since June, 2012 by assessing the needs of users of Milwaukee County’s existing, analog public safety radio system; by drafting a conceptual design for its replacement; by developing the procurement specifications for the digital, Project 25 trunked simulcast radio system that has become known as OASIS; and by providing consulting services to support the initial stages of the deployment of the OASIS network.

Mr. Steve Surwillo is one of CDX Wireless’ Principal consultants and he has 23 years of experience in the field of public safety radio communications.  He holds a Bachelor’s of Science in Electrical Engineering, a Master’s of Science in Information Technology, and the credential of Project Management Professional (PMP).

Mr. Surwillo will hold overall responsibility for completing the Scope of Work described in this Project Scope.  He will be CDX Wireless’ single point of contact for this project and any additional project staff will report through him.

Mr. Surwillo will be supported by other CDX Wireless in tasks such as providing expertise in specific technical areas related to public safety radio communications or preparing and assembling deliverables and reports.

# Place of Performance

CDX Wireless’ work on this project will include a combination of off-site and on-site activities, the latter occurring at the offices of CDX Wireless.  CDX Wireless shall be on-site as is practically necessary to complete the Scope of Work described below with the expectation that this shall entail approximately two (2) to three (3) days of on-site presence approximately one to two times per month, however, the on-site schedule will be adjusted as necessary to accommodate the completion of tasks.  When their nature allows, meetings or other project-related discussions will be conducted via phone conference or WebEx telepresence.

# Scope of Work

## Background

Milwaukee County has entered into an Agreement with Motorola Solutions, Inc. (“Motorola”) under which Motorola will design, construct, install, optimize, test, and otherwise implement a new Public Safety Digital Trunked Radio System for Milwaukee County.  This system is to be interconnected with a similar system being provided by Motorola to Waukesha County and the two Counties’ systems (known together as OASIS) will be interconnected via a Shared Core.  Motorola and Milwaukee County have the responsibilities to complete the system implementation as described in the Statement of Work included in Contract for Service #1332 as executed by Motorola and Milwaukee County.

This Scope of Work from CDX Wireless includes tasks that span the entire project as well ask tasks that correspond directly to the activities of Motorola that had definitive start and completion milestone dates.

The tasks that span the entire project are:

- Project Administration, including

  - Project Management

  - Vendor Contract Management

- Governance Development and Maintenance

- Outreach Development and Delivery

The tasks that correlate to Motorola project milestones are:

- Kickoff

- Site Acquisition / Zoning

- Order Processing 1

- Licensing

- Manufacture (Fixed Network Equipment, Subscribers) 1

- Staging and Factory Acceptance Test Plan 1

- Fleetmap

- Subscriber Flash Inventory

- Civil Work Site Development

- Installation: Antennas/Line

- Installation: FNE

- Console Installation

- Control Station Installation

- System Optimization

- Training

- Site Audit

- Acceptance Testing: Functional

- Acceptance Testing: Coverage

- Cutover

- Finalize

- Optional: Subscriber Installation Management

- Optional: MCTS Project Management

## Work Activities

The following table describes the activities and responsibilities of CDX Wireless along with the expected activities and responsibilities of Milwaukee County and Motorola.  NOTE: This table lists only those tasks that have not yet been completed.

| Project Task | Activities & Responsibilities of CDX Wireless | Activities & Responsibilities of Motorola | Activities & Responsibilities of Milwaukee County |
| --- | --- | --- | --- |
| Tasks that span the entire project |
| Project Administration Including: Project Management Vendor Contract Management | Prepare for and attend project status updates and project reviews. Identify to Milwaukee County and Motorola project issues and risks and cooperatively work with all to identify and resolve/mitigate them. Cooperatively work with Motorola and Milwaukee County to review the need for project changes and, when warranted, assist in the development of change orders and/or contract amendments to include listings of changes to project scope/performance, schedule, and cost. | Call, prepare agenda (and other materials for) and lead project status updates and reviews. Cooperatively work with Milwaukee County and CDX Wireless and Milwaukee to raise and clearly identify project issues and risks and resolve/mitigate them. Cooperatively work with Milwaukee County and CDX Wireless and Milwaukee to review the need for project changes and, when warranted, support the development of change orders and/or contract amendments to include listings of changes to project scope/performance, schedule, and cost. | Prepare for and attend project status updates and project reviews. Actively participate in discussions regarding project issues and risks and cooperatively work with all to identify and resolve/mitigate them. Cooperatively work with Motorola and CDX Wireless to review the need for project changes and, when warranted, assist in the development of and be ultimately responsible for the approval of change orders and/or contract amendments to include listings of changes to project scope/performance, schedule, and cost. |
| Governance Development & Maintenance | Assist in the development of agreements, memorandums-of-understanding, cost models, participation plans, and other similar documents regarding the cooperative deployment, operation/maintenance, and use of the system. Prepare drafts of such documents and assist in their negotiation and/or finalization with system partners (other Shared Core owners), site-owners, system users/participants, and vendors. Review drafts of similar documents prepared by Milwaukee County. Research best-practices (from other similar projects, industry associations, and government organizations) related to such documents and advise on their impact to Milwaukee County. Attend and support on-going meetings of governance boards or committees and provide subject matter expertise to their proceedings, including to subcommittees and/or working groups. | Provide input on the impact of relevant portions of governance documents to system performance, cost, or schedule. | Identify the need for and scope of agreements, memorandums-of-understanding, cost models, participation plans, and other similar documents regarding the cooperative deployment, operation/maintenance, and use of the system. Provide reviews and revisions to drafts prepared by CDX Wireless. Lead negotiations with system partners (other Shared Core owners), site-owners, system users/participants, and vendors and be ultimately responsible for the approval of governance documents. When necessary, provide input (such as existing documents or local regulatory support) to governance documents to be developed by CDX Wireless. |
| Outreach Development & Delivery | Assist in the development of descriptions, presentations, position papers, procedures, and similar documents to be used to describe the deployment, operation/maintenance, and use of the system to groups within Milwaukee County including the Milwaukee County Office of Emergency Management, other departments within Milwaukee County, and potential or confirmed municipal-level system participants. Prepare drafts of such documents and assist in their finalization as well as the delivery of such outreach materials to their audiences. Research best-practices (from other similar projects, industry associations, and government organizations) related to such documents and advise on their impact to Milwaukee County. | Provide input on the impact of relevant portions of outreach documents to system performance, cost, or schedule. | Identify the need for and scope of outreach documents regarding the cooperative deployment, operation/maintenance, and use of the system. Provide reviews, revisions, and approvals to drafts prepared by CDX Wireless. Lead the delivery of such documents to system partners (other Shared Core owners), system users/participants, and vendors. When necessary, provide input to outreach documents to be developed by CDX Wireless. |
| Tasks that correlate to Motorola milestones |
| Site Acquisition / Zoning | Assist in the identification and evaluation of sites to be used. Review technical information provided by Motorola. Lead the preparation of leases or other agreements needed to prepare the sites for remediation and/or occupancy. | Provide technical information regarding the system’s requirements for site space, electrical power, HVAC, and other resources. Identify issues that must be addressed as part of leases/agreements and that must be remediated prior to occupancy. | Identify the sites to be used in the project. Assist in the preparation of leases or other agreements needed for site remediation and/or occupancy. Execute such leases or other agreements. |
| Licensing | Complete the licensing activities as included in CDX Wireless’ Contract for Service # 1235 with Waukesha County (according to which CDX Wireless shall prepare the licensing documents for the 800MHz P25 channels to be used in the OASIS system). | Provide technical information as required to complete the licensing process. (Also, complete the licensing of frequencies required for use by the microwave system.) | Review, approve, and submit licensing documents prepared by CDX Wireless. Pay related coordination and licensing fees. |
| Fleetmap | Gather required contents for a fleetmap from Motorola. Provide assistance to Milwaukee County to assemble draft of fleetmap to include: List of talkgroups Naming conventions Talkgroup ID plan Talkgroup system parameters Radio ID plan Subscriber talkgroup layout Subscriber programming parameters Other items necessary to configure system and subscribers Assist the County in arranging meetings with user agencies to review and edit the contracts of the draft fleetmap. Participate in those meetings. Assist in review of final fleetmap contents. | Identify the required contents of a fleetmap. Provide technical information to Milwaukee County and CDX Wireless, in order to assemble draft of fleetmap to include: List of talkgroups Naming conventions Talkgroup ID plan Talkgroup system parameters Radio ID plan Subscriber talkgroup layout Subscriber programming parameters Other items necessary to configure system and subscribers Review final fleetmap contents. Use fleetmap results to program system. | Lead the effort, with assistance from Motorola and CDX Wireless, to assemble draft of fleetmap to include: List of talkgroups Naming conventions Talkgroup ID plan Talkgroup system parameters Radio ID plan Subscriber talkgroup layout Subscriber programming parameters Other items necessary to configure system and subscribers Arrange for meetings with user agencies to review and edit the contracts of the draft fleetmap. Finalize fleetmap contents and share with Motorola and subscriber-programming organizations (shops). |
| Subscriber Flash Inventory | Assist in the development of inventory for “Flash” upgradeable radios. Assist the County in arranging meetings with user agencies to review and edit the contracts of the draft fleetmap. Participate in those meetings. | Prepare an initial inventory of the current Flash versions in Motorola radios held by municipal agencies. Order Flashes for upgrades to Motorola radios as identified by the final Flash inventory. Provide those Flash upgrades to Milwaukee County (or designated programming shop). | Prepare an initial inventory of the current Flash versions in Motorola radios held by Milwaukee County departments. Arrange for meetings with user agencies to review and edit the contracts of the draft fleetmap. Finalize the inventory of current Flash versions for Motorola radios held by municipal agencies and Milwaukee County departments. Provide the final Flash inventory to Motorola. |
| Civil Work Site Development | Review and provide comments regarding drawings and permit applications. As necessary, observe construction and installation of shelters and towers. Provide assistance, as requested, for interconnection or changes with utilities. Assist in the development of applications for permits (utility, construction, building) and FAA filings (if relevant). Identify and coordinate the acquisition of drawings, specifications, or other details for such permits. Review completion of Motorola’s tasks regarding Civil Work Site Development and provide comments to Milwaukee County. | Prepare site construction drawings, including conduct surveys (ground and tower) and soil borings. Gain regulatory approvals for sites (NEPA, etc.). Assist in the development of applications for permits (utility, construction, building) and FAA filings (if relevant). Provide drawings, specifications, or other details for such permits. Clear and grade site for construction and complete installation of shelters/towers as contracted (see Statement of Work from Contract for Service #1332 for site-by-site details). Complete site improvements (facilities, electrical, grounding, etc.) as contracted (see Statement of Work from Contract for Service #1332 for site-by-site details). Connect sites to utilities. | Complete Site Acquisition services as described above. Ensure Motorola has access to sites. Assemble and submit applications for permits (utility, construction, building) and FAA filings (if relevant Submit permit applications and pay fees. Observe construction and installation of shelters and towers. Arrange for interconnection or changes, as necessary, with utilities. Approve completion of Motorola’s tasks regarding Civil Work Site Development. |
| Installation: Antennas/Line | As necessary, observe installation of antennas and lines. Review completion of Motorola’s tasks regarding Antenna and Line Installation and provide comments to Milwaukee County. | Install antennas and lines as contracted (see Statement of Work from Contract for Service #1332 for site-by-site details). | Ensure Motorola has access to sites. Observe installation of antennas and lines. Approve completion of Motorola’s tasks regarding Antenna and Line Installation. |
| Installation: Fixed Network Equipment | As necessary, observe installation of Fixed Network Equipment (FNE). Review completion of Motorola’s tasks regarding FNE and provide comments to Milwaukee County. | Install equipment at sites as contracted (see Statement of Work from Contract for Service #1332 for site-by-site details). Complete/modify site drawings according to installation. Interconnect new equipment to existing (analog) system as required per contract. Remove existing (analog) system equipment as available. | Ensure Motorola has access to sites. Observe installation of system equipment Approve completion of Motorola’s tasks regarding FNE Installation. |
| Console Installation – For County Departments | Assist in the development of the user-interface of new consoles. Observe installation of console equipment. Assist County in providing dispatch connectivity that meets system specifications (including act as interface to connectivity supplier). Review completion of Motorola’s tasks regarding console equipment and provide comments to Milwaukee County. Assist in integration of logging recorders including CVDS recorders at MCEMS and MCTS. | Assist in the development of the user-interface of new consoles. Install equipment at sites as contracted (see Statement of Work from Contract for Service #1332 for site-by-site details). Program and configure consoles per user-interface requirements. Provide dispatch connectivity specifications and test county-provided connectivity. Perform console programming per templates (see Fleetmapping). Provide integration services to logging recorders including licenses and integration support to CVDS recorders at MCEMS and MCTS. | Arrange for user meetings to identify the user-interface of new consoles. Ensure Motorola has access to console locations. Provide dispatch connectivity that meets system specifications (including act as interface to connectivity supplier). Observe installation of console equipment. Approve completion of Motorola’s tasks regarding Console Installation. Acquire from Motorola necessary integration services (including licenses) to logging recorders including CVDS recorders at MCEMS and MCTS. |
| Console Installation – For Municipal Agencies (Assumes municipal agencies will be ultimately responsible for procuring and installing their dispatch consoles.) | Provide municipal agencies with technical requirements and timing for console connections to the OASIS Shared Core. Work with municipal agencies and Motorola to coordinate the schedule and logistics of their console interconnection to the OASIS Shared Core. | Identify technical requirements for console connections to the OASIS Shared Core. Work with municipal agencies to coordinate the schedule and logistics of their console interconnection to the OASIS Shared Core. | Work with municipal agencies and Motorola to coordinate the schedule and logistics of their console interconnection to the OASIS Shared Core. |
| Control Station Installation | Assist County in identifying areas of concern (and possible improvements) to ensure control station environments meet requirements of Statement of Work from Contract for Service #1332 (proper wall feed-through, ground point, ample space, power outlet, etc.). As necessary, observe installation of control station equipment. Review completion of Motorola’s tasks regarding console equipment and provide comments to Milwaukee County. | Conduct surveys and develop preparation plans for control station installations. Install control station equipment, including RF and other cabling, at sites as contracted (see Statement of Work from Contract for Service #1332 for site-by-site details). Perform control station programming per templates (see Fleetmapping). | Ensure Motorola has access to control station locations. Provide control station environment that meets requirements of Statement of Work from Contract for Service #1332 (proper wall feed-through, ground point, ample space, power outlet, etc.). Observe installation of control station equipment. Approve completion of Motorola’s tasks regarding Control Station Installation. |
| System Optimization | Assist in gathering/ developing information about subscriber fleet (radio ID’s, talkgroup ID’s, etc.) to facilitate system programming. As necessary, observe programming of system equipment. Assist in resolution of any issues related to interfaces/ links that are provided by third parties. Review completion of Motorola’s tasks regarding system optimization and provide comments to Milwaukee County. | Program system equipment using County-provided information about subscriber fleet (radio ID’s, talkgroup ID’s, etc.). Integrate, optimize, and verify the interfaces between equipment, sites, consoles, and other system components. Test features and functionality to verify performance. Test links between sites and provide results to County. | Ensure Motorola has access to sites. Provide information about subscriber fleet (radio ID’s, talkgroup ID’s, etc.) to facilitate system programming. Observe programming of system equipment. Resolve any issues related to interfaces/links that are provided by third parties. Approve completion of Motorola’s tasks regarding system optimization. |
| Training | Assist in review and approval of Motorola-provided training materials. Assist in provision of training facilities for local classes. As needed, attend Motorola’s facilities for all classes. | Develop and present training materials. Prepare training schedules. Deliver training per requirements of Statement of Work from Contract for Service #1332. | Review and approve training materials. Provide training facilities for local classes. Attend Motorola’s facilities for vendor-location classes. |
| Site Audit | Assist in review reports of deficiencies as related to “R56” standards. Assist in identification of plans to rectify site deficiencies. Assist in review and approval of site remediation. | Perform audits of site to identify deficiencies as related to Motorola “R56” standards for communications sites. Report on deficiencies and provide costs to remediate. Remediate sites as agreed-to by County. | Provide access to sites. Review reports of deficiencies as related to “R56” standards. Approve plans to remediate site deficiencies. Review and approve site rectification. |
| Acceptance Testing: Functional | Assist in preparation of test plans for functional testing of system. Oversee conduct of functional testing plans. Assist in review and approval of documented list of testing issues or deficiencies. Assist in review and approval of resolved issues or deficiencies or alternate resolution plan. | Prepare test plans for functional testing of system. Conduct functional testing per approved test plans. Document and rectify any issues or deficiencies arising from conduct of test plan. Resolve issues and retest or agree to alternate resolution plan. | Approve test plans for functional testing of system. Oversee conduct of functional testing plans. Review and approve of documented list of testing issues or deficiencies. Review and approve of resolved issues or deficiencies or alternate resolution plan. |
| Acceptance Testing: Coverage | Assist in preparation of test plans for coverage testing of system. Oversee conduct of coverage testing plans (act as a test driver/witness). Assist in review and approval of documented list of testing issues or deficiencies. Assist in review and approval of resolved issues or deficiencies or alternate resolution plan. | Prepare test plans for coverage testing of system. Conduct coverage testing per approved test plans. Document and rectify any issues or deficiencies arising from conduct of test plan. Resolve issues and retest or agree to alternate resolution plan. | Approve test plans for coverage testing of system. Oversee conduct of coverage testing plans. Provide the necessary number of test vehicles and drivers/witnesses. Review and approve of documented list of testing issues or deficiencies. Review and approve of resolved issues or deficiencies or alternate resolution plan. |
| Cutover | Assist in development of cutover plan. Assist in dissemination of cutover plan to user agencies. Assist in tracking of readiness of user agencies. Assist in delivery of outreach and guidance to user agencies to promote readiness. Attend cutover meetings and assist in provision of updates on user agency cutover activities. | Develop cutover plan. Execute cutover plan and hold cutover meetings to coordinate activities. | Assist in development of cutover plan. Disseminate cutover plan to user agencies. Track readiness of user agencies. Conduct outreach and provide guidance to user agencies to promote readiness. Attend cutover meetings and provide updates on user agency cutover activities. |
| Finalize | Identify punch-list items, work to resolve them, report on resolution progress. Assist in review and approval of Customer Support Plan. Assist in review and approval of final project documentation. | Identify punch-list items, work to resolve them, report on resolution progress. Develop Customer Support Plan. Identify and provide final project documentation. | Identify punch-list items, work to resolve them, report on resolution progress. Review and approve Customer Support Plan. Review and approve final project documentation. |
| Subscriber Installation | OPTIONAL: Provision of Subscriber Installation services is not included in this Scope of Work. The following description of activities to be performed is illustrative of the work that CDX Wireless is available to perform pending further discussion and a review to this Scope of Work, including a revisions to pricing. |
|  | Assist in the approval of operation of test subscribers per templates. Assist in the development and approval of mobile radio installation template. Assist in the coordination of delivery of radios (including vehicles for mobile radios) to be programmed and/or “Flash” upgraded. | Program and verify operation of test subscriber radios per templates. Program radio fleets per approved templates. Provide and perform “Flash” upgrades for upgradeable radios. Develop mobile radio installation template. Install mobile radios in vehicles. | Approve operation of test subscribers per templates. Approve mobile radio installation template. Coordinate delivery of radios (including vehicles for mobile radios) to be programmed and/or “Flash” upgraded. |
| MCTS Deployment Management | OPTIONAL: Provision of Deployment Management services to the Milwaukee County Transit System (MCTS) is not included in this Scope of Work. The following description of activities to be performed is illustrative of the work that CDX Wireless is available to perform pending further discussion and a review to this Scope of Work, including a revisions to pricing. |
|  | Coordinate and oversee the integration of MCTS’ computer aided dispatch (CAD) and in-bus integrated vehicle logic unit (IVLU) equipment to the new OASIS radio system. Coordinate the logistics and provision of buses for programming, upgrades, and installations of software or hardware to operate on the new OASIS radio system. | Provide technical assistance as needed to integrate MCTS’ computer aided dispatch (CAD) and in-bus integrated vehicle logic unit (IVLU) equipment to the new OASIS radio system. | Contract with the vendors of MCTS’ computer aided dispatch (CAD) and in-bus integrated vehicle logic unit (IVLU) equipment for the necessary hardware, software, and services to interface to the new OASIS radio system. |

## Schedule of Work

CDX Wireless, Motorola, and Milwaukee County have developed the following OASIS Project Schedule (dated April 10, 2015) and CDX Wireless assumes that the conduct of Work Activities will occur according to it.

# Price Quotation

## Quotation Basis

The following price quotation is based on the provision of staffing according to the Project Staffing, Place of Performance, and Scope of Work (including Schedule of Work) as described above.  Work Breakdown and Labor Quotation

CDX Wireless has developed the following work breakdown to list the total number of hours of labor required to complete the Scope of Work described above.  These quantities of hours of labor, and the corresponding labor costs, are quoted as not-to-exceed amounts.  CDX Wireless shall invoice Milwaukee County, and Milwaukee County shall pay CDX Wireless, only for those hours actually expended by CDX Wireless.  CDX Wireless shall not invoice Milwaukee County, and Milwaukee County shall not pay CDX Wireless, for hours of labor beyond those listed in the following work breakdown unless both parties agree to revise the work breakdown based on a change to the required level of staffing, the scope of project tasks, or the duration of the project schedule that has occurred for reasons outside of the control of CDX Wireless.  CDX Wireless shall not invoice Milwaukee County, and Milwaukee County shall not pay CDX Wireless, for hours of labor not expended by CDX Wireless.

The following work breakdown and price quotation is exclusive of those tasks identified as “Optional”.

| Project Task | # of Labor Hours | Cost Per Hour | Total Labor Cost |
| --- | --- | --- | --- |
| Tasks that span the entire project (from May 2015 to June 2016) |
| Project Administration Including: (16 hours per month for 14 months) | 224 hours | $135.00 | $30,240 |
| Governance Development & Maintenance (8 hours per month for 14 months) | 112 hours | $135.00 | $15,120 |
| Outreach Development & Delivery (8 hours per month for 14 months) | 112 hours | $135.00 | $15,120 |
| Tasks that correlate to Motorola milestones |
| Site Acquisition | 24 hours | $135.00 | $3,240 |
| Licensing | n/a | $135.00 | $0 |
| Fleetmap | 40 hours | $135.00 | $5,400 |
| Subscriber Flash Inventory | 40 hours | $135.00 | $5,400 |
| Civil Work Site Development | 16 hours | $135.00 | $2,160 |
| Installation: Antennas/Line | 16 hours | $135.00 | $2,160 |
| Installation: Fixed Network Equipment | 16 hours | $135.00 | $2,160 |
| Console Installation – For County Departments | 64 hours | $135.00 | $8,640 |
| Console Installation – For Municipal Agencies | 40 hours | $135.00 | $5,400 |
| Control Station Installation | 8 hours | $135.00 | $1,080 |
| System Optimization | 32 hours | $135.00 | $4,320 |
| Training | 64 hours | $135.00 | $8,640 |
| Site Audit | 16 hours | $135.00 | $2,160 |
| Acceptance Testing: Functional | 64 hours | $135.00 | $8,640 |
| Acceptance Testing: Coverage | 80 hours | $135.00 | $10,800 |
| Cutover (12 hours per month for 8 months) | 96 hours | $135.00 | $12,960 |
| Finalize | 16 hours | $135.00 | $2,160 |
| Labor Total | 1,080 hours |  | $145,800 |

## Travel and Other Expenses

Milwaukee County shall reimburse CDX Wireless for the actual costs of travel required to perform the Scope of Work described above.  Reimbursed costs shall be limited to air fare, lodging (when required), rental cars (including fuel), meals, and airport parking.  The costs of meals shall be limited to General Services Administration’s Per Deim rates and shall exclude lunch and incidentals.

For planning purposes, CDX Wireless expects incur travel costs an average of twice per month for 14 months and expects an average of $800 per each travel occurrence, resulting in an estimated project-total cost of travel of $22,400.

Milwaukee County shall reimburse CDX Wireless for the actual costs of third-party materials and services required to perform the Scope of Work described above.  Unless approved in advance and in writing by Milwaukee County, such materials and services shall be limited to the production or reproduction of documents.

## Invoicing

CDX Wireless shall submit to Milwaukee County each month an invoice detailing:

- The period of performance (i.e., the month in which labor was expended and costs were incurred)

- The number of hours expended that month for each task

- The number of hours remaining for each task (after that month’s labor expenditures)

- The total labor cost for that month

- The total of travel and other costs incurred that month (along with of receipts, invoices, or other justification for all travel or other costs for which CDX Wireless seeks reimbursement)

- The total cost of labor and expenses for that period (i.e., the invoice total)

These tasks have been completed.

CDX Wireless’ work on this activity for Milwaukee County is covered under a separate contract (Contract for Service #1235 between CDX Wireless and Waukesha County).

This scope of work is only inclusive of Motorola-provided voice dispatch consoles to the Milwaukee County 9-1-1 Center, the Milwaukee County Emergency Medical Service Telecommunicator’s Center, and the Milwaukee County Transit System’s (MCTS’) Dispatch Center.  It is exclusive of integration of MCTS’ Computer Aided Dispatch system.

This scope of work is only inclusive of Motorola-provided voice dispatch consoles to the Milwaukee County 9-1-1 Center, the Milwaukee County Emergency Medical Service Telecommunicator’s Center, and the Milwaukee County Transit System’s (MCTS’) Dispatch Center.  It is exclusive of integration of MCTS’ Computer Aided Dispatch system.