File No. 11-30(a)(a)/11-108

(Journal, December 16, 2010)

(ITEM 7) Reference file established by the County Board Chairman, relative to Sales of Park East Lands, by recommending adoption of the following:

A RESOLUTION

WHEREAS; RSC & Associates (“RSC”) closed on the purchase of Block 26 in December 20007 and the County was paid the $2,725,000 purchase price.  RSC was prepared to break ground on the Park East Square project (“Project”) when the economic downturn resulted in the Project lender rescinding RSC’s loan commitment, with the result being the construction timeline in the Project Development Agreement cannot be met until replacement financing is secured; and

WHEREAS, in a letter dated February 18, 2011, RSC indicated they have pursued numerous types of financing alternatives, including conventional lending through banks, pension funds, insurance companies, Disaster Recovery Bonds and WHEDA housing tax credits, with Common Bond Communities (“Common Bond”) as a partner.  RSC states that unfortunately these various funding alternatives have not materialized or are not entirely feasible financing options in this economic climate,   since even those apartment projects that have advanced recently have done so with GAP loans or loan guarantees; and

WHEREAS, RSC recognizes that time and continued perseverance is needed to find the final solution and therefore is requesting an extension to the Excavation Commencement Date until September 30, 2011 and sixty days thereafter for the Excavation Completion date.  As a result, an amendment to the Development Agreement (“Fifth Amendment”) is necessary.  County staff, Corporation Counsel and private legal counsel, enlisted by Corporation Counsel, has worked with RSC to establish the following summary terms and conditions of the Fifth Amendment to the Development Agreement:

- The Project Excavation Commencement Date, defined in the original Development Agreement with Milwaukee County, be extended from March 30, 2010 to September 30, 2011  and 60 days thereafter for the Excavation Completion Date.

- RSC has now forfeited to the County the entire $50,000 in the Letter of Credit for not meeting the prior Excavation Completion Dates and the Letter of Credit will be refunded by RSC to the original $50,000 prior to the Excavation Commencement Date.

- In the event RSC fails to achieve the September 30, 2011 Excavation Commencement Date and the Excavation Completion Date 60-days thereafter, the County shall be entitled to all the remedies, rights, terms and conditions accruing in the Development Agreement, including without limitation, a $2,000/day penalty and the County’s option to repurchase Block 26 at 85% of what the County was paid.

- Except a provided above, the terms and conditions of the Fifth Amendment to the Development Agreement of Block 26 would be substantially the same as the terms and conditions of the original Development Agreement; and

WHEREAS, in this extraordinary economic and lending environment, the successful completion of the RSC Project for Block 26 will lead to increased jobs, tax base and be a catalyst for further development in and in proximity to the Park East Corridor; and

WHEREAS, the Committee on Economic and Community Development, at its meeting on March 7, 2011, recommended approval of the above-described Fifth Amendment; now, therefore,

BE IT RESOLVED, the County Executive and the County Clerk are hereby authorized to execute, after Corporation Counsel approval, the above-described Fifth Amendment to the Development Agreement for Block 26 in the Park East Corridor.