## Bud Rev Sum
[16 empty] | Approved | Fund | Number of
[6 empty] | GARB | PFC BACKED | INTEREST | STATE | FEDERAL | PFC | CAPITAL |  | TOTAL |  | by way of | Transfer | Fund
Project # | Project Name | Manager | Proj Approved. |  | Proj Complete | BONDS | BONDS | ON BONDS | GRANT | GRANT | REVENUE | RESERVE | Other | FUNDING |  | Capital Budget | Revisions | Transfers
[6 empty] | A/C 4907 | A/C 4907 | A/C 1841 | A/C 2299 | A/C 2699 | A/C 4901
ACTIVE GMIA PROJECTS
WA005 | Master Plan Update | Kevin Demitros | 2001-07-19 | Transfer | 2013 | 0 | 0 | 0 | 0 | 0 | 1787160 | 0 | 0 | 1787160 |  | 0 | 1787160 | 4 | 1
WA006 | C Concourse, Four Gate Expansion | Ed Baisch | 1999 | Adopted budget | 2010 | 0 | 59586365.72 | 1079000 | 0 | 0 | 3992853 | 583300 |  | 65241518.72 |  | 32915070 | 32326448.72 | 15 | 1
WA022 | Abrasive Storage Building- Design | Paul Montalto | 2009-09-15 | Budget | 2012 | 0 | 0 | 0 | 283757.5 | 1702545 | 283757.5 | 0 | 0 | 2270060 |  | 2270060 | 0
WA042 | Baggage Claim Remodeling | Jim Zsebe | 2006 | Adopted Budget | 2014 | 0 | 0 | 0 | 0 | 0 | 7131750 | 0 | 0 | 7131750 |  | 7131750 | 0
WA044 | In-line Bag Screening, Phase 1 and 2 | Tim Kipp | 2002 | Adopted Budget | 2013 | 0 | 26236300 | 289500 | 393312 | 17289018 | 7880000 | 0 | 0 | 52088130 |  | 26565800 | 25522330 | 1 | 1
WA048 | D Concourse Improvements | Ed Baisch | 2003 | Adopted Budget | 2012 | 0 | 10791950 | 318000 | 0 | 0 | 8522630 | 375000 | 0 | 20007580 |  | 10084950 | 9922630 | 6 | 1 | 1 | 1 | 1
WA061 | E Concourse Stem Remodeling & Electrical | Ed Baisch | 2004 | Adopted Budget | 2011 | 9455299 | 17000 | 4000 | 0 | 0 | 350000 | 1204000 | 0 | 11030299 |  | 9455299 | 1575000 | 2
WA064 | Phase II Mitigation Program | Kim Berry | 2009-09-15 | Budget | 2014 | 0 | 0 | 0 | 2775260 | 22202080 | 2775260 | 0 | 0 | 27752600 |  | 27752600 | 0
WA072 | LJT Runway Crack Repair and Sealcoating | Paul Montalto | 2006 | Adopted Budget | 2012 | 0 | 0 | 0 | 59525 | 2135220 | 35750 | 25775 | 0 | 2256270 |  | 1979270 | 277000 | 3 | 1 | 1 | 1
WA094 | Runway Safety Area Improvements - RSA-Runway 1L, 19R, 7R and 25L - Design | Jim Zsebe | 2005 | Adopted Budget | 2013 | 0 | 10711184 | 0 | 8624434 | 53736604 | 947750 | 0 | 0 | 74019972 |  | 58316831 | 15703141 | 3 | 1 | 1 | 1 | 1 | 1 | 1
WA095 | Terminal Cable Tray System | Wilfredo Rivera | 2009-09-15 | transfer | 2011 | 0 | 0 | 0 | 0 | 0 | 0 | 347000 | 0 | 347000 |  |  | 347000 | 1
WA096 | Parking Structure Relighting | Tim Kipp | 2009-09-15 | transfer | 2012 | 0 | 1616000 | 0 | 0 | 0 | 195000 | 0 | 0 | 1811000 |  | 1616000 | 195000 | 1
WA100 | Security Sys Fiber Optic Cable Replacement | Steve Dragosz | 2006-11-07 | adopted budget | 2010 | 0 | 0 | 0 | 186375 | 1118250 | 522375 | 0 | 0 | 1827000 |  | 1827000 | 0
WA108 | HVAC Equipment Replacement | V. Mehla | 2006-05-31 | Budget | 2011 | 6412700 | 0 | 46700 | 0 | 0 | 0 | 400000 | 0 | 6859400 |  | 5933150 | 926250 | 1 | 1
WA122 | Airfield Pavement Rehabilitation | Paul Montalto | 2006-11-07 | adopted budget | 2012 | 0 | 0 | 0 | 552625 | 3315750 | 816725 | 490000 |  | 5175100 |  | 4325100 | 850000 | 1 | 1
WA123 | Airfield Safety Improvements | Tim Kipp | 2006-11-07 | adopted budget | 2012 | 0 | 0 | 0 | 289500 | 1737000 | 165250 | 128250 | 0 | 2320000 |  | 2320000 | 0 | 1
WA124 | Install Ground Power Units& Preconditioned Air | Ed Baisch | 2007-11-03 | Adopted Budget | 2011 | 0 | 0 | 0 | 278625 | 1923750 | 288025 | 0 | 0 | 2490400 |  | 1269400 | 1221000 | 1 | 1
WA125 | Security and Wildlife Perimeter Fence | Paul Montalto | 2007-11-03 | Adopted Budget | 2012 | 0 | 0 | 0 | 147750 | 886500 | 147200 | 0 | 0 | 1181450 |  | 866450 | 315000 | 2 | 1 | 1
WA127 | GMIA Terminal Expansion Design Study | Mac Malas | 2007-11-03 | Adopted Budget | 2016 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 500000 |  | 500000 | 0
WA130 | Noise Barrier Study | Kim Berry | 2007-11-03 | Adopted Budget | 2011 | 0 | 0 | 0 | 35510 | 284080 | 36410 | 0 | 0 | 356000 |  | 180900 | 175100 | 1
WA131 | Part 150: Ramp Electrification | Ed Baisch | 2007-11-03 | Adopted Budget | 2012 | 0 | 0 | 0 | 50562 | 357375 | 50063 | 0 | 0 | 458000 |  | 458000 | 0
WA133 | D Hammerhead Restroom Remodel | J. Zsebe | 2008-11-11 | Adopted Budget | 2012 | 2190000 |  | 0 | 0 | 0 | 221000 | 0 | 0 | 2411000 |  | 221000 | 2190000 | 1 | 1
WA135 | Runway 1L/19R & 7R/25L Intersection | Ed Baisch | 2008-10-08 | Transfer | 2013 | 0 | 0 | 0 | 1709045 | 10244184 | 1688229 | 0 | 0 | 13641458 |  | 8750000 | 4891458 | 1 | 1 | 1
WA139 | Redundant Main Electrical Feed | Jim Zsebe | 2008-11-11 | Adopted Budget | 2013 | 0 | 160500 | 0 | 0 | 0 | 4184000 | 3702500 | 0 | 8047000 |  | 8047000 | 0
WA141 | Admin BLDG Ground Level Build Out GMIA TRAINING FACILITY | Bernie Mielcarek | 2008-11-11 | Adopted Budget | 2013 | 2415000 |  | 0 | 0 | 0 | 0 | 489000 | 0 | 2904000 |  | 2904000 | 0
WA142 | LJT Runway 15L - 33R Extension | Ed Baisch | 2008-11-11 | Adopted Budget | 2011 | 0 |  | 0 | 13450 | 511100 | 0 | 13450 | 0 | 538000 |  | 538000 | 0
WA145 | Runway Guard Lights | T. Kipp | 2008-11-11 | Transfers | 2012 | 1648000 |  | 0 | 168000 | 1008000 | 168000 | 0 | 0 | 2992000 |  | 0 | 2992000 | 2 | 1 | 1
WA147 | Deicing pads at Cargo | Jim Zsebe | 2011 | Transfers | 2013 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 100000 |  |  | 100000 | 1 | 1
WA148 | Expand Fleet Building | Paul Montalto | 2010-01-01 | Budget | 2012 | 0 |  | 0 | 0 | 0 | 3616000 | 0 | 0 | 3616000 |  | 3366000 | 250000 | 1
WA149 | Snow Equipment Storage Building | Jim Zsebe | 2010-01-01 | Budget | 2012 | 0 | 13272000 | 0 | 0 | 0 | 330000 | 0 | 0 | 13602000 |  | 13272000 | 330000 | 1
WA151 | Part 150 Noise Monitoring | Kim Berry | 2013 | Budget | 2013 | 0 | 0 | 0 | 214000 | 1712000 | 214000 | 0 | 0 | 2140000 |  | 1850000 | 290000 | 1
WA152 | Part 150 Vacant land Acquisition | Kim Berry | 2009 | Budget | 2012 | 0 | 0 | 0 | 156000 | 1248000 | 156000 | 0 | 0 | 1560000 | 0 | 1040000 | 520000 | 1
WA153 | Purchase Non-County owned jet bridges | Tom Heller | 2012 | Budget | 2014 | 3000000 | 2000000 | 0 | 0 | 0 | 5500000 | 0 | 0 | 10500000 |  | 6550000 | 3950000 | 1 | 1
WA158 | GMIA Deicing Pad | Tim Kipp | 2013 | Budget | 2013 | 0 |  | 0 | 0 | 0 | 300000 | 0 | 0 | 300000 |  | 300000 | 0
WA160 | GMIA Narrow Band Conversion | Terry Blue | 2011 | Budget | 2013 | 2000000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2000000 |  | 2000000 | 0 |  | 1
WA161 | GMIA Terminal Roadway Signage | Bernie Mielcarek | 2011 | Budget | 2013 | 0 |  | 0 | 0 | 0 | 3100000 | 0 | 0 | 3100000 |  | 3100000 | 0
WA162 | GMIA CESSNA SERVICE APRON RECONSTRUCTION | Paul Montalto | 2012 | Budget | 2013 | 0 |  | 0 | 139500 | 837000 | 11875 | 127625 | 0 | 1116000 |  | 1116000 | 0
WA163 | GMIA PERIMETER ROAD BRIDGE OVER HOWELL AVENUE | Karl Stave | 2012 | Budget | 2013 | 0 |  | 0 | 750000 | 4500000 | 750000 | 0 | 0 | 6000000 |  | 3500000 | 2500000 | 1
WA165 | Taxiway B Reconstruction | Tim Kipp | 2011 | Budget | 2012 | 0 |  | 0 | 2373600 | 0 | 0 | 593400 | 0 | 2967000 |  | 2140000 | 827000 | 2 | 1 | 1
WA166 | GMIA Perimeter Road Extension | Tim Kipp | 2012-01-01 | Adopted Budget | 2013 | 0 |  | 0 | 137500 | 825000 | 137500 | 0 |  | 1100000 |  | 1100000 | 0
WA167 | GMIA Terminal Escalator Replacement | Pete Asfari | 2012-01-01 | Adopted Budget | 2013 | 0 |  | 0 | 0 | 0 | 0 | 600000 | 0 | 600000 |  | 600000 | 0
WA169 | LJT Runway and Taxiway Lights | Paul Montalto | 2012-01-01 | Adopted Budget | 2013 | 0 |  | 0 | 6250 | 237500 | 0 | 6250 |  | 250000 |  | 250000 | 0
WA173 | GMIA Fuel Farm Electrical Service | Mary Turner | 2012-01-01 | Adopted Budget | 2013 | 0 |  | 0 | 0 | 0 | 0 | 150000 | 0 | 150000 |  | 150000 | 0
WA175 | GMIA Concourse C Checkpoint | Ed Baisch | 2011 | Fund Transfer | 2013 | 0 |  | 0 | 0 | 0 | 0 | 472000 | 0 | 472000 |  |  | 472000 | 1 | 1
| Data shown is as of end of June 2012 |  | Grand total GMIA Projects |  |  | 27120999 | 124391299.72 | 1737200 | 19344580.5 | 127810956 | 56904562.5 | 9707550 | 0 | 367017147.72 | 0 | 256561630 | 110455517.72 | 57
0
Formulas:
Proj Approved. = +'[1]WA005'!E4
Proj Approved. = +'[1]WA022'!D4
Note on A103: sdyett: There are rows hidden here

## Summary view 3
[6 empty] | Capital | Fund | Number of | Amounts per Advantage |  |  |  |  | Expedition | Currently | Future | Net
[6 empty] | Budget | Transfer | Fund | Cumulative | Cumulative | Cumulative | Currently | Available | Remaining | Uncommited | Commitments | Available
Project # | Project Name | Manager | Proj Approved. |  | Proj Complete | Approved | Revisions | Transfers | Budget | Expended | Unrealized | Encumbered | Funds | Commitments | Funds | Per A&E
[14 empty] | Note A |  | Note B
ACTIVE GMIA PROJECTS
WA005 | Master Plan Update | Kevin Demitros | 2001-07-19 | Transfer | 2013 | 0 | 1624824 | 3 | 1787160 | 1775399.1 | 11760.9 | 0 | 11760.9 | -0.1 | 11761 | 11760 | 1
WA006 | C Concourse, Four Gate Expansion | Ed Baisch | 1999 | Adopted budget | 2010 | 32621612 | 32678963 | 14 | 65241518.72 | 64318517.86 | 923000.86 | 28256.75 | 894744.11 | 0.39 | 894743.72 | 169402 | 725341.72
WA022 | Abrasive Storage Building- Design | Paul Montalto | 2009-09-15 | Budget | 2012 |  |  |  | 2270060 | 261611.9 | 2008448.1 | 318500.01 | 1689948.09 | 0.09 | 1689948 | 1687738 | 2210
WA042 | Baggage Claim Remodeling | Jim Zsebe | 2006 | Adopted Budget | 2014 | 7131750 | 0 | 1 | 7131750 | 3598458.28 | 3533291.72 | 2384719.87 | 1148571.85 | 821.85 | 1147750 | 999429 | 148321
WA044 | In-line Bag Screening, Phase 1 and 2 | Tim Kipp | 2002 | Adopted Budget | 2013 | 52088133 |  |  | 52088130 | 34035741.24 | 18052388.76 | 9345352.68 | 24690388.56 | 15609314 | 9081074.56 | 0 | 9081074.56
WA048 | D Concourse Improvements | Ed Baisch | 2003 | Adopted Budget | 2012 | 10084950 | 7065164 | 5 | 20007580 | 18539494.88 | 1468085.12 | 10255 | 1457830.12 | 9820.12 | 1448010 | 74971 | 1373039
WA061 | E Concourse Stem Remodeling & Electrical | Ed Baisch | 2004 | Adopted Budget | 2011 | 9455299 | 1575000 | 3 | 11030299 | 10677224.08 | 353074.92 | 27707.19 | 325367.73 | 6842.73 | 318525 | 316932 | 1593
WA064 | Phase II Mitigation Program | Kim Berry | 2009-09-15 | Budget | 2014 |  |  |  | 27752600 | 9964878.99 | 17787721.01 | 2556450.78 | 15231270.23 | 0.23 | 15231270 | 14218270 | 1013000
WA072 | LJT Runway Crack Repair and Sealcoating | Paul Montalto | 2006 | Adopted Budget | 2012 | 399168 | -55000 | 1 | 2256270 | 1038601.71 | 1217668.29 | 247806.24 | 969862.05 | 1040210.1 | 232729 | 232729 | 0
WA094 | Runway Safety Area Improvements - RSA-Runway 1L, 19R, 7R and 25L - Design | Jim Zsebe | 2005 | Adopted Budget | 2013 | 500000 | 582000 | 1 | 74019972 | 59813714.76 | 14206257.24 | 10005353.84 | 4200903.4 | 141982.4 | 4058921 | 4023616 | 35305
WA095 | Terminal Cable Tray System | Wilfredo Rivera | 2009-09-15 | transfer | 2011 |  |  |  | 347000 | 266258.08 | 80741.92 | 11617.76 | 69124.16 | 34316.16 | 34808 | 14153 | 20655
WA096 | Parking Structure Relighting | Tim Kipp | 2009-09-15 | transfer | 2012 |  |  |  | 1811000 | 363511.82 | 1447488.18 | 57623.36 | 1389864.82 | 431078 | 958786.82 | 958787 | -0.18
WA100 | Security Sys Fiber Optic Cable Replacement | Steve Dragosz | 2006-11-07 | adopted budget | 2010 |  |  |  | 1827000 | 1721861.06 | 105138.94 | 0 | 105138.94 | -0.06 | 105139 | 105139 | 0
WA108 | HVAC Equipment Replacement | V. Mehla | 2006-05-31 | Budget | 2011 | 400000 | 0 | 0 | 6859400 | 6624245.03 | 235154.97 | 0 | 235154.97 | 99027.97 | 136127 | 106297 | 29830
WA122 | Airfield Pavement Rehabilitation | Paul Montalto | 2006-11-07 | adopted budget | 2012 | 200000 |  |  | 5175100 | 4053208.47 | 1121891.53 | 967052.12 | 154839.41 | 10118.41 | 144721 | 68263 | 76458
WA123 | Airfield Safety Improvements | Tim Kipp | 2006-11-07 | adopted budget | 2012 |  |  |  | 2320000 | 2284229.49 | 35770.51 | 0 | 35770.51 | 0 | 35770.51 | 17570 | 18200.51
WA124 | Install Ground Power Units& Preconditioned Air | Ed Baisch | 2007-11-03 | Adopted Budget | 2011 |  |  |  | 2490400 | 1011651.81 | 1478748.19 | 408113.67 | 1070634.52 | 93182.52 | 977452 | 975209 | 2243
WA125 | Security and Wildlife Perimeter Fence | Paul Montalto | 2007-11-03 | Adopted Budget | 2012 |  |  |  | 1181450 | 773248.11 | 408201.89 | 162868.6 | 245333.29 | 8525.29 | 236808 | 236763 | 45
WA127 | GMIA Terminal Expansion Design Study | Mac Malas | 2007-11-03 | Adopted Budget | 2016 | 500000 |  |  | 500000 | 0 | 500000 | 0 | 500000 | 0 | 500000 |  | 500000
WA130 | Noise Barrier Study | Kim Berry | 2007-11-03 | Adopted Budget | 2011 |  |  |  | 356000 | 1000 | 355000 | 0 | 355000 | 0 | 355000 | 355000 | 0
WA131 | Part 150: Ramp Electrification | Ed Baisch | 2007-11-03 | Adopted Budget | 2012 | 458000 |  |  | 458000 | 0 | 458000 | 0 | 458000 | 0 | 458000 | 458000 | 0
WA133 | D Hammerhead Restroom Remodel | J. Zsebe | 2008-11-11 | Adopted Budget | 2012 |  |  |  | 2411000 | 1174723.33 | 1236276.67 | 59184.3 | 1177092.37 | 0.37 | 1177092 | 1177092 | 0
WA135 | Runway 1L/19R & 7R/25L Intersection | Ed Baisch | 2008-10-08 | Transfer | 2013 |  |  |  | 13641458 | 5825559.07 | 7815898.93 | 4834596.59 | 4037912.88 | 20588.34 | 4017324.54 | 2707139 | 1310185.54
WA139 | Redundant Main Electrical Feed | Jim Zsebe | 2008-11-11 | Adopted Budget | 2013 | 8047000 |  |  | 8047000 | 428274.9 | 7618725.1 | 36829.88 | 7581895.22 | 836.22 | 7581059 | 7561331 | 19728
WA141 | Admin BLDG Ground Level Build Out GMIA TRAINING FACILITY | Bernie Mielcarek | 2008-11-11 | Adopted Budget | 2013 | 2905805 |  |  | 2904000 | 97362.84 | 2806637.16 | 0 | 2754132.88 | 9024.88 | 2745108 | 2740728 | 4380
WA142 | LJT Runway 15L - 33R Extension | Ed Baisch | 2008-11-11 | Adopted Budget | 2011 | 538000 |  |  | 538000 | 172682.13 | 365317.87 | 30158.36 | 335159.51 | 28808.51 | 306351 | 306351 | 0
WA145 | Runway Guard Lights | T. Kipp | 2008-11-11 | Transfers | 2012 |  |  |  | 2992000 | 1107072.06 | 1884927.94 | 0 | 1884927.94 | 11717.94 | 1873210 | 225210 | 1648000
WA147 | Deicing pads at Cargo | Jim Zsebe | 2011 | Transfers | 2013 |  |  |  | 100000 | 15526.68 | 84473.32 | 0 | 84473.32 | 0.32 | 84473 | 84473 | 0
WA148 | Expand Fleet Building | Paul Montalto | 2010-01-01 | Budget | 2012 |  |  |  | 3616000 | 445966.97 | 3170033.03 | 341635.01 | 2828398.02 | 0.02 | 2828398 | 2821660 | 6738
WA149 | Snow Equipment Storage Building | Jim Zsebe | 2010-01-01 | Budget | 2012 |  |  |  | 13602000 | 576337.92 | 13025662.08 | 494559.99 | 12531102.09 | 0.09 | 12531102 | 12530513 | 589
WA151 | Part 150 Noise Monitoring | Kim Berry | 2010 | Adopted Budget | 2013 |  |  |  | 2140000 | 0 | 2140000 | 0 | 2140000 | 0 | 2140000 | 2140000 | 0
WA152 | Part 150 Vacant land Acquisition | Kim Berry | 2010 | Adopted Budget | 2012 |  |  |  | 1560000 | 0 | 1560000 | 0 | 1560000 | 0 | 1560000 | 1560000 | 0
WA153 | Purchase Non-County owned jet bridges | Tom Heller | 2010 | Transfer 2009 | 2014 | 10500000 |  |  | 10500000 | 1825260 | 8674740 | 0 | 8674740 | 0 | 8674740 | 8674740 | 0
WA158 | GMIA Deicing Pad | Paul Montalto | 2013 | Budget | 2013 |  |  |  | 300000 | 0 | 300000 | 0 | 300000 | 0 | 300000 | 275000 | 25000
WA160 | GMIA Narrow Band Conversion | Terry Blue | 2010 | Budget | 2013 |  |  |  | 2000000 | 1663167.26 | 336832.74 | 89552.32 | 247280.42 | 0.42 | 247280 | 0 | 247280 | est.
WA161 | GMIA Terminal Roadway Signage | Bernie Mielcarek | 2011 | Budget | 2013 | 3100000 |  |  | 3100000 | 143244.81 | 2956755.19 | 137445 | 2819310.19 | 70893.19 | 2748417 | 2748417 | 0
WA162 | GMIA CESSNA SERVICE APRON RECONSTRUCTION | Paul Montalto | 2012 | Budget | 2013 | 1116000 |  |  | 1116000 | 0 | 1116000 | 0 | 1116000 | 75000 | 1041000 | 1041000 | 0
WA163 | GMIA PERIMETER ROAD BRIDGE OVER HOWELL AVENUE | Karl Stave | 2012 | Budget | 2013 | 3500000 |  |  | 6000000 | 403005.06 | 5596994.94 | 113742.31 | 5483252.63 | 0.63 | 5483252 | 5472508 | 10744
WA165 | Taxiway B Reconstruction | Tim Kipp | 2011 | Budget | 2012 |  |  |  | 2967000 | 2736360.86 | 230639.14 | 4551.22 | 226087.92 | -320.08 | 226408 | 226308 | 100
WA166 | GMIA Perimeter Road Extension | Tim Kipp | 2012-01-01 | Adopted Budget | 2013 | 1100000 |  |  | 1100000 | 26519.22 | 1073480.78 | 12808.15 | 1060672.63 | 19450.63 | 1041222 | 1028804 | 12418
WA167 | GMIA Terminal Escalator Replacement | Pete Asfari | 2012-01-01 | Adopted Budget | 2013 | 600000 |  |  | 600000 | 237.6 | 599762.4 | 0 | 599762.4 | 11449.4 | 588313 | 587957 | 356
WA169 | LJT Runway and Taxiway Lights | Paul Montalto | 2012-01-01 | Adopted Budget | 2013 | 250000 |  |  | 250000 | 0 | 250000 | 763.73 | 249236.27 | 20219.27 | 229017 | 228232 | 785
WA173 | GMIA Fuel Farm Electrical Service | Mary Turner | 2012-01-01 | Adopted Budget | 2013 | 150000 |  |  | 150000 | 0 | 150000 | 0 | 150000 | 75000 | 75000 | 75000 | 0
WA175 | GMIA Concourse C Checkpoint | Ed Baisch | 2011 | Fund Transfer | 2013 |  |  |  | 472000 | 313075.05 | 158924.95 | 73921.8 | 85003.15 | 14775.15 | 70228 | 67711 | 2517
Data shown is as of end of June 2012 |  | Grand total GMIA Projects |  |  |  | . |  |  | 367017147.72 | 238077232.43 | 128939915.29 | 32761426.53 | 113165947.5 | 17842685.4 | 95626339.15 | 79310202 | 16316137.15
Note A: | Defined as total commitments per Expedition, less expenditures to date and less encumbrances
In other words, planned future expenditures not yet recognized in Advantage.
Note B: | Estimates by A&E of future commitments, not yet in either Advantage or Expedition.
These are being picked up as uncommitted funds as per Project Listing report
Note VV: | Refinement of estimated commitments or accounting JV will eliminate any shortfall.
Formulas:
Proj Approved. = +'[1]WA005'!E4
Proj Approved. = +'[1]WA022'!D4