Milwaukee County

# Meeting Agenda

County Courthouse 901 N. 9th Street, Rm. 105

Milwaukee, WI 53233

# Sustainability Task Force

# (Steering Group)

# Aging and Disabilities Services - Marietta Luster;                                                                                                                        Community Reintegration Center - Shawn Sullivan;                                                                                                                            County Parks - Guy Smith & Sarah Toomsen;                                                                                                                                           Dept. of Transportation - John Blonien, Ryan Donnelly & Michelle Dasse (John Rodgers alt.);                                                       Emergency Management - Paul Reigel;                                                                                                                                               Facilities Management - Stu Carron & Grant Helle (Co-Chairs);                                                                                                                      Office of Equity – Sumaiyah Clark (interim);                                                                                                                                                                  Office of Strategy, Budget and Performance - Heather Wolfgram & Isaac Rowlett;                                                                            Milwaukee County Transit Services - Natalie Marshall;                                                                                                                 Milwaukee County Zoo - Kari Williams (Matt Haseman alt.)

April 19, 2024			2:00 – 3:00 PM			Via Teleconference

Virtual meeting via Microsoft Teams and teleconference

Phone: 414-436-3530 United States, Milwaukee (Toll)

Conference ID: 295 852 292 151 #

Public comments will be taken at the discretion of the Chair.

* Action item

### Call to Order & Roll Call

### Present (4 voting members):	G. Smith, S. Clark, N. Marshall, and K. Williams

### Excused: 			S. Toomsen, M. Dasse, S. Carron, H. Wolfgram, I. Rowlett, P. Reigel, and

### J. Rodgers

### Guests: 				Gordie Bennett and Madison Humphry (Office of Sustainability)

### County Supervisors Anne O’Connor and Steven Shea

### Approval of Meeting Minutes*

### Attachment:	Draft Meeting Minutes 20240212

### This item was NOT DISCUSSED due to a lack of quorum.

### Climate Action 2050 (CA50) Updates (formerly item #4)

### Presented by G. Bennett, Sustainability Director.

### Attachment:	CA50 Planning Updates 20240419

### Notes: The Office of Sustainability (OS) is coordinating delivery of the CA50 Plan. OS has requested additional ARPA funding to procure another consultant for research and analysis, stakeholder engage, and plan design and layout.

### Due to termination of original planning consultant, additional time will be needed to deliver a successful CA50 Plan. Gordie suggests pushing back the target plan completion date from June 2024 to May 2025. Under this revised timeline, the final plan would be published in April 2025 and submitted for County Board review and approval during the May 2025 meeting cycle. Gordie will reach out to Task Force members to ask whether they can serve beyond the original commitment date (June 2024).

### Along with Facilities Director and Planning and Development Director, OS held ‘Sustainability Planning’ meetings with county departments from February-April 2024 (see slide 4 of the attached presentation). Purpose of the meetings was to explore how the CA50 Plan can support depts.’ priorities and plans.

### Gordie shared a list of community meetings OS is planning for the remainder of the planning process (see slide 5 of the presentation). Guy thinks that the Youth Commission will be particularly interested in discussing CA50 strategies. Sumaiyah asked how community input will be documented and incorporated into the CA50 Plan. Gordie offered to summarize and share the community input OS receives with the Task Force. Gordie requested the Task Force’s help with ensuring CA50 Plan deliverables reflect the community’s concerns and needs.

### Guest Sup. Shea asked how have community members reacted to CA50 planning thus far? Gordie responded that turnout to community events has been mixed but OS has received some helpful feedback. As OS reported to the County Board, the online survey the former planning consultants administered in January 2023 received 700+ responses but several inner-city zip codes were under-represented. To counter this, the consultants hosted two workshops in these areas during May 2023.

### To help keep CA50 planning rooted in health-equity, guest Sup. O’Connor encourages the Task Force to review the work of the Fair Futures environmental justice group.

### This item was DISCUSSED WITH NO ACTION TAKEN.

### CA50 Strategy Development (formerly item #5)

### Presented by G. Bennett, Sustainability Director.

### Attachment:	CA50 Planning Updates 20240419

### Notes: Gordie shared a list of themes from the ‘Sustainability Planning’ meetings with county depts. (see item #3 and slide 11 of the attached presentation). He asked the Task Force which themes are most related to CA50 principles & goals, and which ones resonate the most for them or their depts. Guy said that four themes resonate for County Parks: land restoration, net zero buildings, right sizing portfolio, and salt and chemical reduction. Kari likes the idea of further exploring solar PV and EV chargers, as well as sustainable building standards. Guest Sup. Shea would like to see Milwaukee County do more solar PV installations and net zero buildings.

### This item was DISCUSSED WITH NO ACTION TAKEN.

### EV Planning Internship Updates (formerly item #3)

### Presented by M. Humphry, EV Planning Intern for the Office of Sustainability.

### Attachment:	EV Planning Internship Update

### Notes: UWM graduate student Madison Humphry shared her progress and updates on a comprehensive guidebook for Milwaukee County which aims to boost electric vehicle (EV) adoption and infrastructure while prioritizing health and equity. She identified disparities in charging access, concerns over vehicle affordability and safety, and gaps in consumer awareness. She shared recommendations that encompass EV charger standards, case studies for four Milwaukee County owned properties, feasible locations for EVSE implementation and public charging, public-private partnerships, design considerations, education initiatives, and progress metrics. Madison invited members to contribute input and recommendations for the final presentation on May 17 (1:00-2:00pm).

### This item was DISCUSSED WITH NO ACTION TAKEN.

### 2023 Emissions Inventory & Forecast

### This item was DISCUSSED as part of #3 WITH NO ACTION TAKEN.

### Next Meeting: May 17, 2024, from 2:00 – 3:00 pm

### Adjourn