| Task | Description | Completion Date | Timeframe | Responsible Person(s) |
| --- | --- | --- | --- | --- |
| 1 | Project Team members present the proposed path forward using an incremental decision-making approach to the Parks and/or Finance Committees, depending on the Chairwoman’s referrals (submit report in early or mid-August) | September 14, 2021 (Parks) | Seven weeks | Project Team Dept. Leaders (support) |
| 2 | Select vendors to perform independent reviews for discrete components of the Domes project including the funding stack and partnership structure (contracts will be under $50,000; no RFP is required). Contracts will include required meetings with project team members and/or technical experts within Milwaukee County. | November 30, 2021 | Eight weeks | Review Team Dept. Leaders (support) Procurement (support) |
| 3 | Project Team members provide an update to the Parks Committee (submit report in early November) | December 7, 2021 | --- | Project Team Dept. Leaders (support) |
| 4 | Contracts completed for the vendors; work begins | December 14, 2021 | Two weeks from selection | Respective Department Staff Procurement (support) |
| 5 | Vendors submit preliminary reports to Milwaukee County (meetings with Milwaukee County staff to occur throughout the development of the reports) | February 25, 2022 | Approx. ten weeks from beginning of contract period | Review Team Respective Department Staff Project Team |
| 6 | Project Team members provide an update to the Parks Committee (submit report by February 18) | March 24, 2022 | --- | Project Team Dept. Leaders (support) Vendors (as requested) |
| 7 | Vendors submit final reports to Milwaukee County (meetings with Milwaukee County staff to occur throughout the development of the reports) | March 30, 2022 | Approx. fourteen weeks from beginning of contract period | Review Team Respective Department Staff Project Team |
| 8 | Anticipated conclusion of the Glazing System Renovation Investigation and Safety Mesh Inspection and Repairs Projects | March 30, 2022 | --- | Facilities Management Division |
| 9 | Department staff and Project Team review final vendor reports and present findings to Dept. Leaders and Administration | April 27, 2022 | Four weeks from final vendor report | Review Team Respective Department Staff Project Team |
| 10 | Engage with County residents to discuss the path forward and process through a series of in-person and virtual meetings in conjunction with the Board of Supervisors | March 1-April 26, 2022 | Seven weeks | Project Team Dept. Leaders Administration Supervisors |
| 11 | Project Team summarizes the community engagement outcomes | May 24, 2022 | Four weeks | Project Team |
| 12 | Project Team presents updated recommendations to Dept. Leaders and Administration for review and approval | June 21, 2022 | Four weeks | Project Team Dept. Leaders Administration |
| 13 | Anticipated updated repair cost estimates upon receiving the consultant’s report and recommendations from the glazing system (“mock-up”) testing | June 30, 2022 | --- | Facilities Management Division |
| 14 | Project Team members report final recommendations on the path forward for the Domes to the Parks Committee (submit report in early or mid-June) | July 2022 Post-April 2022 committee meeting dates not yet available | Approx. four weeks | Project Team Dept. Leaders/Administration |
| 15 | Board approval of path forward for the Domes | September 2022 (after August recess) Post-April 2022 Board meeting dates not yet available | Approx. eight-ten weeks from Parks Committee vote | Board of Supervisors |
| Capital project timeline to be determined. |

KEY

Project Team Items

Facilities Management Division Items

Committee and Board of Supervisors Items