## Summary view 3
[6 empty] | Capital | Fund | Number of | Amounts Per Advantage |  |  |  |  | Expedition | Currently | Future | Net
[6 empty] | Budget | Transfer | Fund | Cumulative | Cumulative | Cumulative | Currently | Available | Remaining | Uncommited | Commitments | Available
Project # | Project Name | Manager | Proj Approved. |  | Proj Complete | Approved | Revisions | Transfers | Budget | Expended | Unrealized | Encumbered | Funds | Commitments | Funds | Per A&E
[14 empty] | Note A |  | Note B
ACTIVE GMIA PROJECTS
WA005 | Master Plan Update | Kevin Demitros | 2001 | Transfer | 2013 | 0 | 1624824 | 3
WA042 | Baggage Claim Remodeling | Jim Zsebe | 2006 | Adopted Budget | 2015 | 7131750 | 0 | 1 | 53154000 | 32564128.18 | 20589871.82 | 10669415.46 | 9920456.36 | 10338522.82 | 10251353 | 10251353 | 0
WA044 | In-line Bag Screening, Phase 1 and 2 | Tim Kipp | 2002 | Adopted Budget | 2015 | 52088133 |  |  | 49273130 | 37848051.71 | 11425078.29 | 730228.92 | 10694849.37 | 1566791.29 | 9128058.08 | 836562.37 | 8291495.71
WA064 | Phase II Mitigation Program | Kim Berry | 2009 | Adopted Budget | 2015 |  |  |  | 55972600 | 46495469.39 | 9477130.61 | 2447803.42 | 7029327.19 | 565514 | 6463813.19 | 6463813.19 | 0
WA072 | LJT Runway Crack Repair and Sealcoating | Ed Baisch | 2006 | Adopted Budget | 2014 | 399168 | -55000 | 1 | 2256270 | 1528153.32 | 728116.68 | 0 | 728116.68 | 0 | 728116.68 | 0 | 728116.68
WA094 | Runway Safety Area Improvements - RSA-Runway 1L, 19R, 7R and 25L - Design | Jim Zsebe | 2005 | Adopted Budget | 2015 | 500000 | 582000 | 1 | 74019972 | 72225413.7 | 1794558.3 | 0 | 1794558.3 | 0 | 1794558.3 | 0 | 1794558.3
WA095 | Terminal Cable Tray System | Tim Kipp | 2009 | Transfer | 2015 |  |  |  | 347000 | 324639.68 | 22360.32 | 0 | 22360.32 | 0 | 22360.32 | 0 | 22360.32
WA096 | Parking Structure Relighting | Tim Kipp | 2009 | Transfer | 2015 |  |  |  | 1811000 | 1531320.32 | 279679.68 | 57914.33 | 221765.35 | 58005 | 163760.35 | 163760 | 0.35
WA112 | GMIA Taxiway R & R3 Reconstruction | Ed Baisch | 2012 | Adopted Budget | TBD |  |  |  | 400000 | 156.89 | 399843.11 | 0 | 399843.11 | 51843.11 | 348000 | 348000 | 0
WA122 | Airfield Pavement Rehabilitation | Tim Kipp | 2006 | Adopted Budget | 2015 | 200000 |  |  | 7295100 | 7073790.06 | 221309.94 | 119362.44 | 101947.5 | 99403.94 | 2543.56 | 2544 | -0.44
WA123 | Airfield Safety Improvements | Tim Kipp | 2006 | Adopted Budget | 2015 |  |  |  | 3863000 | 3668287.06 | 194712.94 | 149216.88 | 45496.06 | 0 | 45496.06 | 45496 | 0.06
WA125 | Security and Wildlife Perimeter Fence | Anthony Raab | 2007 | Adopted Budget | 2015 |  |  |  | 1743450 | 1393973.41 | 349476.59 | 189150.84 | 160325.75 | 76818 | 83507.75 | 83508 | -0.25
WA127 | GMIA Terminal Expansion Design Study | Ed Baisch | 2007 | Adopted budget | 2016 | 500000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WA130 | Noise Barrier Study | Kim Berry | 2008 | Adopted Budget | 2015 |  |  |  | 356000 | 245527.47 | 110472.53 | 104838.53 | 5634 | 0 | 5634 | 5634 | 0
WA131 | Part 150: Ramp Electrification | Ed Baisch | 2007 | Adopted Budget | TBD | 458000 |  |  | 458000 | 0 | 458000 | 0 | 458000 | 0 | 458000 | 458000 | 0
WA139 | Redundant Main Electrical Feed | Mary Turner | 2008 | Adopted Budget | 2015 | 8047000 |  |  | 7565500 | 7545802.05 | 19697.95 | 19698 | -0.05 | 0 | -0.05 | 0 | -0.05
WA141 | Admin BLDG Ground Level Build Out GMIA Training Facility | Bernie Mielcarek | 2008 | Adopted Budget | 2015 | 2905805 |  |  | 2904000 | 2566471.35 | 337528.65 | 14017.34 | 323511.31 | 12613 | 310898.31 | 310898 | 0.31
WA147 | Deicing pads at Cargo | Jim Zsebe | 2011 | Transfer | TBD |  |  |  | 100000 | 15526.68 | 84473.32 | 0 | 84473.32 | 0.32 | 84473 | 84473 | 0
WA148 | Expand Fleet Building | Anthony Raab | 2010 | Adopted Budget | 2015 |  |  |  | 3616000 | 1039905.15 | 2576094.85 | 79804.88 | 2496289.97 | 0 | 2496289.97 | 320000 | 2176289.97
WA151 | Part 150 Noise Monitoring | Kim Berry | 2010 | Adopted Budget | 2015 |  |  |  | 2140000 | 0 | 2140000 | 0 | 2140000 | 0 | 2140000 | 2140000 | 0
WA152 | Part 150 Vacant land Acquisition | Kim Berry | 2010 | Adopted Budget | TBD |  |  |  | 1560000 | 0 | 1560000 | 0 | 1560000 | 0 | 1560000 | 1560000 | 0
WA153 | Purchase Non-County owned jet bridges | Jim Zsebe | 2010 | Transfer | 2014 | 10500000 |  |  | 4500000 | 3752224.96 | 747775.04 | 0 | 747775.04 | 0 | 747775.04 | 0 | 747775.04
WA158 | GMIA Deicing Pad Design and Construction | Tim Kipp | 2013 | Adopted Budget | 2015 |  |  |  | 12900000 | 1356541.41 | 11543458.59 | 9989400.66 | 1554057.93 | 1368415.34 | 185642.59 | 185643 | -0.41
WA161 | GMIA Terminal Roadway Signage | Bernie Mielcarek | 2011 | Adopted Budget | 2015 | 3100000 |  |  | 3100000 | 3000269.26 | 99730.74 | 95344.02 | 4386.72 | 19 | 4367.72 | 4368 | -0.28
WA162 | GMIA Cessna Service Apron Reconstruction | Jim Zsebe | 2012 | Adopted Budget | 2015 | 1116000 |  |  | 779500 | 692323.82 | 87176.18 | 41565.51 | 45610.67 | 31308.67 | 14302 | 14302 | 0
WA163 | GMIA Perimeter Road Bridge over Howell Avenue | Karl Stave | 2012 | Adopted Budget | 2015 | 3500000 |  |  | 8950000 | 6813199.84 | 2136800.16 | 1919596.27 | 217203.89 | 1388.89 | 215815 | 215815 | 4.6566e-10
WA167 | GMIA Terminal Escalator Replacement | Anthony Raab | 2012 | Adopted Budget | 2015 | 600000 |  |  | 2550000 | 1538082.25 | 1011917.75 | 800318.8 | 211598.95 | 206275 | 5323.95 | 0 | 5323.95
WA169 | LJT Runway and Taxiway Lights | Tim Kipp | 2012 | Adopted Budget | 2015 | 250000 |  |  | 500000 | 315922.54 | 184077.46 | 11651.45 | 172426.01 | 7634.01 | 164792 | 164792 | 0
WA172 | GMIA terminal Sanitary Sewer Utility Upgrade | Ed Baisch | 2012 | Adopted Budget | 2015 |  |  |  | 600000 | 67499.77 | 532500.23 | 505327.21 | 27173.02 | 27173 | 0.02 | 0 | 0.02
WA173 | GMIA Fuel Farm Electrical Service | Mary Turner | 2014 | Adopted Budget | 2015 | 150000 |  |  | 1100000 | 883676.91 | 216323.09 | 95452.65 | 120870.44 | 99307.09 | 21563.35 | 21563 | 0.35
WA176 | GMIA Airport Master Plan-AGIS/eALP | Ed Baisch | 2012 | Adopted Budget | 2015 | 0 | 0 | 0 | 500000 | 270102.43 | 229897.57 | 23066.88 | 206830.69 | 27703.57 | 179127.12 | 179127 | 0.12
WA177 | GMIA Parking Structure Repairs | Julie Bastin | 2012 | Adopted Budget | 2015 | 0 | 0 | 0 | 959000 | 41900.31 | 917099.69 | 6527.25 | 910572.44 | 84087.44 | 826485 | 826485 | 0
WA178 | GMIA Parking Garage - Rental Car Area (Infill) | Julie Bastin | 2011 | Adopted Budget | 2014 | 0 | 0 | 0 | 1030000 | 972068.6 | 57931.4 | 2750.82 | 55180.58 | -0.42 | 55181 | 53904 | 1277
WA180 | GMIA Runway 7L-25R Resurface | Anthony Raab | 2014 | Adopted Budget | 2015 |  |  |  | 2100000 | 1319939.13 | 780060.87 | 470072.27 | 309988.6 | 3160.6 | 306828 | 306828 | 0
WA181 | LJT Runway 4L-22R Pavement Resurface | Anthony Raab | 2014 | Adopted Budget | 2015 |  |  |  | 1300000 | 16521.49 | 1283478.51 | 0 | 1283478.51 | 54892.51 | 1228586 | 1228586 | 0
WA182 | GMIA Snow Melter | Jim Zsebe | 2013 | Transfer | 2015 |  |  |  | 1290265 | 995046.46 | 295218.54 | 65896.74 | 229321.8 | 0 | 229321.8 | 229322 | -0.2
WA184 | GMIA -ADS-B Squitter Transponders | Terry Blue | 2013 | Transfer | 2015 |  |  |  | 562500 | 536344 | 26156 | 0 | 26156 | 0 | 26156 | 26156 | 0
WA185 | GMIA Surveillance System | Timothy Kipp | 2013 | Transfer | 2016 |  |  |  | 10200000 | 104397.41 | 10095602.59 | 1033601.93 | 9062000.66 | 55010.66 | 9006990 | 9006990 | 0
WA186 | HVAC Retrocommisioning | Vijay Mehta | 2014 | Transfer | 2015 |  |  |  | 755500 | 283441.55 | 472058.45 | 58876.5 | 413181.95 | 5324.95 | 407857 | 407857 | 0
WA201 | GMIA Terminal Expansion - Center Checkpoint | Ed Baisch | 2014 | Transfer | 2015 |  |  |  | 222000 | 54168.2 | 167831.8 | 129790.5 | 38041.3 | 9550.3 | 28491 | 28491 | 0
Data shown is as of end of December 31, 2014 |  | Grand total GMIA Projects |  |  |  | . |  |  | 322733787 | 239080286.76 | 83653500.24 | 29830690.5 | 53822809.74 | 14750762.09 | 49741467.11 | 35974270.56 | 13767196.55
Note A: | Defined as total commitments per Expedition, less expenditures to date and less encumbrances
In other words, planned future expenditures not yet recognized in Advantage.
Note B: | Estimates by A&E of future commitments, not yet in either Advantage or Expedition.
These are being picked up as uncommitted funds as per Project Listing report