## Sheet3
DAS Facilities Management Division AE&ES Staffing Plan
2016 Adopted Capital Improvements
Milwaukee County
|  |  |  | SIGNATURE |  | DATE | DATE | DATE | COUNTY | DESIGN |  |  |  | CONSTRUCTION MANAGEMENT
|  |  |  | AUTHORITY |  |  |  |  | PROJECT | COUNTY | CNTY & | CONSUL |  | COUNTY | CNTY & | CONSUL
| Sub- |  | 2016 |  |  | Construction Contract Award | Construction Start | Construction Finish | MANAGER | STAFF | CONSUL |  | RFP | STAFF | CONSUL |  | RFP
Proj | Proj | Project Description | Adopted | OWNER | DAS-FM
TRANSPORTATION
Highway and Bridges/Structures
WH010 | WH01002 | Mill Rd. 43rd St. to Sydney Pl. | 5350000 | MCDOT |  | 2016-05-10 | 2016-06-15 | 2017-11-01 | Weddle-Henning | [5 empty] | X |  | X
WH010 | WH01008 | Reconstruct CTH "N" South 92nd Street | 250000 | MCDOT |  | 2019-03-01 | 2019-04-01 | 2019-11-01 | Weddle-Henning |  | X |  | X |  | X |  | X
WH010 | WH01016 | Reconst. 13th: Drexel to Rawson | 500000 | MCDOT |  | 2018-01-01 | 2018-04-01 | 2018-11-01 | Weddle-Henning |  | X |  | X |  | X
WH010 | WH01021 | W. St. Martins Rd S. N Cape Rd to S Lvrs Lane Rd | 3418000 | MCDOT |  | 2016-04-01 | 2016-05-01 | 2016-11-01 | Weddle-Henning | [5 empty] | X |  | X
WH010 | WH01022 | Reconstruct, S. 13th St. Puetz to Drexel | 300000 | MCDOT |  | 2019-02-01 | 2019-04-01 | 2019-11-01 | Weddle-Henning |  | X |  | X |  | X |  | X
WH030 | WH03014 | W. Vienna Ave. - Menomonee River #771 | 150000 | MCDOT |  | 2018-05-01 | 2018-06-01 | 2018-11-01 | Weddle-Henning |  | X |  | X |  | X |  | X
WH090 | WH09001 | West Ryan Road (CTH H) - S 96th St to S 112th St | 90000 | MCDOT |  | 2017-04-01 | 2017-05-01 | 2017-11-01 | Weddle-Henning |  | X |  | X |  | X |  | X
WH091 | WH09101 | Short Term CTH Rehabilitation-Maint. Projects | 450000 | MCDOT |  | 2016-06-01 | 2016-07-01 | 2016-10-01 | Weddle-Henning |  | X |  |  | X
WH097 | WH09701 | E. North Ave Bridge over Oak Leaf Bike Trail | 200000 | MCDOT |  | 2019-03-01 | 2019-04-01 | 2019-09-01 | Weddle-Henning |  | X |  | X |  | X |  | X
WH |  | Highway and Bridges/Structures | 10708000
Transit
WT026 | WT02601 | New Flyer Buses | 14450000 | MCDOT |  | 2016-01-01 |  | 2016-09-01 | Nigh | [5 empty] | X
WT |  | Total Transit | 14450000
Airports
WA125 | WA12501 | GMIA Security and Wildlife Deterrent Perimeter | 309000 |  | X | 2016-05-01 | 2016-06-01 | 2016-11-01 | Raab | X |  |  |  | X
WA177 | WA17701 | GMIA Parking Structure Repairs | 610000 |  | X | 2016-05-01 | 2016-05-01 | 2016-10-01 | Bastin |  | X |  | X |  | X |  | X
WA189 | WA18901 | LJT Airfield Pavement Rehab 2015 | 225000 |  | X | Hold | Hold | Hold | Kipp | X |  |  |  | X
WA190 | WA19001 | LJT Perimeter Security Fence | 225000 |  | X | 2016-05-01 | 2016-06-01 | 2016-10-01 | Raab | X |  |  |  | X
WA191 | WA19101 | GMIA Pavement Rehabilitation 2015 | 1120000 |  | X | 2016-04-01 | 2016-05-01 | 2016-10-01 | Kipp | X |  |  |  | X
WA192 | WA19201 | GMIA Airfield Safety Improvements 2015 | 500000 |  | X | 2016-04-01 | 2016-05-01 | 2016-10-01 | Kipp | X |  |  |  | X
WA194 | WA19401 | GMIA 13-31 and Taxiway S&Y Re-Cable and Relight | 1760000 |  | X | 2016-05-01 | 2016-06-01 | 2016-11-01 | Raab | X |  |  |  | X
WA195 | WA19501 | GMIA Taxiway F Reconstruction | 2500000 |  | X | 2016-07-01 | 2017-04-01 | 2017-11-01 | Hayes | X |  |  |  | X
WA196 | WA19601 | GMIA Replace Skywalk Glass | 5500000 |  | X | 2016-08-01 | 2016-09-01 | 2017-09-01 | Hayes |  |  | X | X | X
WA204 | WA20401 | Part 150 Noise Study Update | 3500000 |  | X | N/A | N/A | N/A | Berry |  |  | X | X | N/A | N/A | N/A
WA205 | WA20501 | GMIA Firehouse Addition - Design & Construction | 1995500 |  | X | 2016-10-01 | 2016-11-01 | 2017-12-01 | Kipp |  |  | X | X | X
WA206 | WA20601 | GMIA Taxi Cab/Grd. Trans. Lot and Restroom | 1584000 |  | X | 2016-05-01 | 2016-06-01 | 2016-11-01 | Hayes |  | X |  | X | X
WA207 | WA20701 | GMIA Landside Road Rehabilitation | 350000 |  | X | 2017-03-01 | 2017-04-01 | 2017-08-01 | Gulgowski | X |  |  |  | X
WA208 | WA20801 | LJT 15L-33R Resurface | 1580000 |  | X | 2016-05-01 | 2017-04-01 | 2017-11-01 | Raab | X |  |  |  | X
WA209 | WA20901 | GMIA Sustainability Master Plan | 400000 |  | X | N/A | N/A | N/A | Hayes |  |  | X | X | N/A | N/A | N/A
WA |  | Total Airport | 22158500
Environmental
WV009 | WV00901 | County-wide Sanitary Sewers Repairs | 150000 |  | X | 2016-08-01 | 2016-10-01 | 2017-06-01 | Stave |  | X |  | X | X
WV022 | WV02201 | Franklin Landfill Infrastructure | 1151000 |  | X | 2016-11-15 | 2017-01-15 | 2017-05-15 | Keith |  |  | X | X |  | X
WV022 | WV02202 | Doyne Landfill Infrastructure | 305000 |  | X | 2016-07-15 | 2016-09-15 | 2016-11-15 | Keith |  |  | X | Annual |  | X
WV |  | Total Environmental | 1606000
|  | Total Transportation and Public Works | 48922500
PARKS, RECREATION AND CULTURE
Milwaukee Public Museum
WM003 | WM00301 | Electrical Distribution Replacement | 1119355 |  | X | 2016-06-01 | 2016-10-01 | 2016-12-01 | Tran |  | X |  | Annual | X
WM |  | Total Milwaukee Public Museum | 1119355
Department of Parks, Recreation & Culture
WP245 | WP24501 | LaFollette Park Playground Replacement | 264200 | PARKS |  | 2016-03-01 | 2016-05-01 | 2016-07-01 | Parks |  | X |  | X | X
WP255 | WP25501 | Sherman Park B&G Club HVAC System Repl. | 1943208 |  | X | 2016-04-01 | 2016-06-01 | 2016-12-01 | Mehta |  | X |  | Annual | X
WP279 | WP27914 | Gordon Park Walkways | 29899 |  | X | 2016-05-01 | 2016-06-01 | 2016-10-01 | Stave | X |  |  |  | X
WP279 | WP27918 | Algonquin Park Walkways | 72244 |  | X | 2016-05-01 | 2016-06-01 | 2016-10-01 | Stave | X |  |  |  | X
WP279 | WP27919 | Bay View Park Walkways | 158902 |  | X | 2016-05-01 | 2016-06-01 | 2016-10-01 | Stave | X |  |  |  | X
WP279 | WP27923 | Kosciuszko Park Walkways | 166943 |  | X | 2016-05-01 | 2016-06-01 | 2016-10-01 | Stave | X |  |  |  | X
WP279 | WP27941 | Big Bay Park Walkways | 72012 |  | X | 2016-05-01 | 2016-06-01 | 2016-10-01 | Stave | X |  |  |  | X
WP290 | WP29001 | Kinnickinnic Parkway- Phase I | 139667 |  | X | Design only | 2017-06-01 | 2017-10-01 | Gulgowski |  | X |  | Annuals | Design only
WP290 | WP29002 | Kinnickinnic Parkway- Phase 2 | 125500 |  | X | Design only | 2017-06-01 | 2017-10-01 | Gulgowski |  | X |  | Annuals | Design only
WP290 | WP29003 | Kinnickinnic Parkway- Phase 3 | 88333 |  | X | Design only | 2018-06-01 | 2018-10-01 | Gulgowski |  | X |  | Annuals | Design only
WP290 | WP29004 | Kinnickinnic Parkway- Phase 4 | 54000 |  | X | Design only | 2018-06-01 | 2018-10-01 | Gulgowski |  | X |  | Annuals | Design only
WP290 | WP29005 | Kinnickinnic Parkway- S. 43rd St. to S. 51st St. | 140833 |  | X | Design only | 2018-06-01 | 2018-10-01 | Gulgowski |  | X |  | Annuals | Design only
WP290 | WP29006 | KK Parkway- Jackson Park Dr 58th-Cleveland | 248667 |  | X | Design only | 2019-06-01 | 2019-10-01 | Gulgowski |  | X |  | Annuals | Design only
WP290 | WP29007 | Kinnickinnic Parkway- S. 29th St. to S. 31st St. | 50500 |  | X | Design only | 2019-06-01 | 2019-10-01 | Gulgowski |  | X |  | Annuals | Design only
WP368 | WP36809 | Brown Deer Clubhouse Roof | 271000 |  | X | 2016-07-01 | 2016-08-01 | 2016-10-01 | Banach |  | X |  | Annual | X
WP491 | WP49101 | East side OLT Reconstruct - Prospect to Bellview | 700000 |  | X | 2016-08-01 | 2016-09-01 | 2016-05-01 | Stave |  | X |  | Annuals |  | X
WP492 | WP49201 | Root River OLT Extension | 1075840 |  | X | 2017-04-01 | 2017-05-01 | 2018-05-01 | Stave |  | X |  | Annuals |  | X
WP610 | WP61001 | Wahl Park Basketball Courts | 200000 |  | X | 2016-05-01 | 2016-06-01 | 2016-08-01 | Gulgowski |  | X |  |  | X
WP613 | WP61301 | Cudahy Park Baseball Diamond | 165600 |  | X | 2016-08-01 | 2016-09-01 | 2017-05-01 | Stave |  | X |  | X |  | X
WP614 | WP61401 | Grant Park Baseball Diamond | 148800 |  | X | 2016-08-01 | 2016-09-01 | 2017-05-01 | Stave |  | X |  | X |  | X
WP616 | WP61601 | Pulaski Park Pavilion Improvements | 130000 |  | X | 2016-08-01 | 2016-09-01 | 2017-01-01 | Freeman |  | X |  | Annual | X
WP617 | WP61701 | Washington Park Baseball Diamond | 210000 |  | X | 2016-08-01 | 2016-09-01 | 2017-05-01 | Stave |  | X |  | X |  | X
WP618 | WP61801 | Washington Park Washington Park Bandshell Maint/Repairs | 738000 |  | X | 2016-09-01 | 2016-10-01 | 2017-04-01 | Adam |  | X |  | Annual | X
WP618 | WP61802 | Washington Park Bandshell Boiler, Ramp, Dehumidifiers | 175000 |  | X | 2016-07-01 | 2016-08-01 | 2017-01-01 | Mehta |  | X |  | Annual | X
WP619 | WP61901 | Milwaukee River Fish Passage | 750000 |  | X | 2016-06-01 | 2016-07-01 | 2017-06-01 | Stave |  |  | X | AECOM |  | X |  | AECOM
WP620 | WP62002 | Wahl Park Pavilion | 200000 |  | X | 2016-08-01 | 2016-09-01 | 2017-01-01 | Freeman |  | X |  | Annual | X
WP |  | Total Department of Parks, Recreation & Culture | 8319148
McKinley Marina
WP512 | WP51201 | McKinley Marina Parking Lots | 365000 |  | X | Design only | 2018-06-01 | 2018-10-01 | Gulgowski |  | X |  | X | Design only
WP |  | Total McKinley Marina | 365000
Zoo
WZ114 | WZ11401 | Zoo Life Support Emergency Generators | 318448 |  | X | 2016-10-01 | 2016-11-01 | 2017-04-01 | Hung |  | X |  | Annual | X
WZ119 | WZ11901 | African Plains Exhibit | 1774000 |  | X | 2016-11-01 | 2017-03-01 | 2018-04-01 | Hung |  | X |  | X | X
WZ150 | WZ15005 | Reconfiguration of POS System- New Admin Fac | 469516 | ZOO |  | 2016-03-01 | 2016-03-01 | 2016-10-01 | Sue Rand |  | X |  | X |  | X
WZ151 | WZ15101 | Aviary Boiler Replacement | 291000 |  | X | 2017-01-01 | 2017-06-01 | 2017-08-01 | Hung |  | X |  | Annual | X
WZ161 | WZ16101 | ARC Ozone SYS Repl/HT EXCH & Chill Valves | 200000 |  | X | 2016-09-01 | 2016-10-01 | 2017-01-01 | Hung |  | X |  | Annual | X
WZ163 | WZ16301 | ARC Heating | 102000 |  | X | 2016-09-01 | 2016-10-01 | 2017-01-01 | Hung |  | X |  | Annual | X
WZ |  | Total Zoo | 3154964
|  | Total Parks Recreation and Culture | 12958467
HEALTH AND HUMAN SERVICES
DHS-Behavioral Health Division
WE |  | Total DHS-Behavioral Health Division | 0
DPW County Grounds
WG |  | Total DPW County Grounds | 0
Department of Human Services
WS040 | WS04010 | McGovern Park Senior Center Fire System | 69030 |  | X | 2016-07-01 | 2016-08-01 | 2016-12-01 | Tran |  | X |  | Annual | X
WS |  | Total Department of Human Services | 69030
|  | Total Health and Human Services | 69030
GENERAL GOVERNMENT
Courthouse Complex
WC059 | WC05901 | CH Complex Electrical Infrastruc Upgrde Phase 1 | 50000 |  | X | 2016-04-01 |  | 2016-11-01 | Tran |  | X |  | Annual | X
WC062 | WC06201 | CJF - Building Roof Replacement | 100000 |  | X | Appropriation for planning and design only |  |  | Freeman |  | X |  | X | X
WC089 | WC08901 | Courthouse Elevator Renovation Phase 1 | 242212 |  | X | 2016-01-01 |  | 2016-05-01 | Waszak |  | X |  | Service | X
WC116 | WC11601 | Courthouse Cooling Coil Replacement | 242000 |  | X | 2016-07-01 | 2016-09-01 | 2016-12-01 | Mehta |  | X |  | Annual | X
WC120 | WC12001 | CJF Hot Water Heater Replacement | 401000 |  | X | 2016-06-01 | 2016-07-01 | 2016-10-01 | Mehta |  | X |  | Annual | X
WC |  | Total Courthouse Complex | 1035212
House of Correction
WJ068 | WJ06801 | HOC Roadway and Sidewalk Replacement | 221000 |  | X | 2016-03-01 | 2016-05-01 | 2016-06-01 | Gulgowski |  | X |  | Annual | X
WJ074 | WJ07401 | HOC Master Control | 804000 |  | X | 2016-12-01 | 2017-01-01 | 2017-05-01 | Banach |  | X |  | X | X
WJ086 | WJ08601 | HOC Visiting Center Safety/Security Improvements | 340000 |  | X | 2016-12-01 | 2017-01-01 | 2017-05-01 | Banach |  | X |  | X | X
WJ |  | Total House of Correction | 1365000
Other County Agencies
WO077 | WO07701 | Oak Creek Parkway- RR Tracks East to Chicago Ave | 80000 |  | X | Design only | 2018-06-01 | 2018-10-01 | Gulgowski |  | X |  | Annual | Design only
WO112 | WO11201 | Fleet General Equipment | 3197000 | MCDOT
WO112 | WO11203 | Sheriff Fleet Equipment | 710000 | MCDOT
WO112 | WO11204 | House of Correction Fleet Equipment | 259000 | MCDOT
WO112 | WO11205 | Fleet Parks Equipment | 2257000 | MCDOT
WO118 | WO11801 | Historical Center Exterior Cornice Restoration | 2000000 |  | X | 2017-01-01 | 2017-03-01 | 2017-09-01 | Schmidt |  | X |  | X | X
WO165 | WO16501 | Countywide ADA Repairs | 500000 |  | X | 2016-08-01 | 2016-09-01 | 2016-11-01 | Freeman |  | X |  | Annual | X
WO217 | WO21701 | Phone and Voicemail Replacement | 250000 | IMSD |  | 2016-03-01 | 2016-05-01 | 2017-12-31 | Wojciechowski |  |  | TDSi | X |  |  | TBD | X
WO246 | WO24601 | Wil O Way Grant Stage Improvements | 62000 |  | X | 2016-09-01 | 2016-10-01 | 2017-01-01 | Adam | X |  |  |  | X
WO247 | WO24701 | MCHS Window Grates | 150000 |  | X | 2017-01-01 | 2017-03-01 | 2017-09-01 | Schmidt |  | X |  | X | X
WO452 | WO45201 | Training Academy-Firing Range Ventillation Sys. | 339494 |  | X | 2016-07-01 | 2016-08-01 | 2016-12-01 | Mehta |  | X |  | Annual | X
WO455 | WO45501 | Training Academy Controlled Turning Target Sys | 335928 |  | X | 2016-08-01 | 2016-09-01 | 2017-01-01 | Banach |  | X |  | Annual | X
WO517 | WO51710 | War Memorial/MAM ADA Restroom Renovations | 333000 |  | X | 2016-08-01 | 2016-09-01 | 2016-12-01 | Bastin |  | X |  | Annual |  | X
WO517 | WO51711 | War Memorial/MAM Electrical System Upgrade | 564000 |  | X | 2016-08-01 | 2016-08-01 | 2016-12-01 | Bastin |  |  | X | X |  | X
WO517 | WO51712 | War Memorial/MAM Sub Basement Structures | 703000 |  | X | 2016-03-01 | 2016-03-01 | 2016-07-01 | Bastin |  | X |  | Annual |  | X
WO517 | WO51714 | Elevator Update and Restoration | 375351 |  | X | 2016-05-01 | 2016-05-01 | 2017-05-01 | Bastin |  |  | X | Annual |  | X
WO602 | WO60201 | Enterprise Platform Modernization | 480000 | IMSD |  | 2016-07-01 | 2017-01-01 | 2018-12-31 | McAllister |  |  | Plante Moran | X |  |  | TBD | X
WO614 | WO61401 | Build Out Ten Sites to Digital | 1559183 | OEM |  | 2016-12-13 | 2016-01-14 | 2016-01-17 | Viel |  |  | Motorola/Baycom |  | X |  | Motorola/Baycom
WO619 | WO61901 | Disaster Recovery Site | 425000 | IMSD |  | 2016-03-01 | 2016-04-01 | 2016-12-31 | Wojciechowski |  |  | Excipio | X |  |  | TBD | X
WO632 | WO63201 | Milwaukee County Internet/Intranet Rebuild/Redes | 450000 | IMSD |  | 2016-04-01 | 2016-05-01 | 2016-12-31 | Carson |  |  | TBD | X
WO948 | WO94801 | Asset and Work Order System | 620000 | IMSD |  | 2016-03-01 | 2016-04-01 | 2016-12-31 | Bahr |  | X | Power Engineers | X |  | X |  | X
WO |  | Total Other County Agencies | 15649956
|  | Total General Government | 18050168
|  | Total Capital Improvements | 80000165