Date:		July 5, 2016

To:		Theodore Lipscomb, Sr., Chairman, County Board of Supervisors

From:		John Dargle, Jr., CPRP, Director, Department of Parks, Recreation and Culture

### Subject:	Update on the Estabrook Dam Rehabilitation – ACTION

# POLICY

Requesting authorization to remove the Estabrook Dam.

# Background

The County is currently under an Administrative Order from the Wisconsin Department of Natural Resources (WDNR) to repair or remove the Estabrook Dam by December 31, 2016. The 2016 Milwaukee County Adopted budget added additional funding to install fish passage accommodations in conjunction with rehabilitation of the dam. Since then, DPRC with the assistance of the Department of Administrative Services – Facilities, AE & ES prepared Construction Documents and solicited bids for the repair of the Estabrook Dam including fish passage.

The following is a summary of the Estabrook Dam Rehabilitation project capital budget:

Total Budget Available (allocations from 2010 to 2016 minus interest)     	$3,352,000

Commitments to date:   Consultant 		                                             -$473,000

AE&ES Services                                               	                         		  -$100,000

Printing, advertise, misc        	                                                          	    -$27,000

Unencumbered Balance                                                                          	$2,752,000

Construction Budget                               					           $2,400,000

Construction contingency (7.5 %+)                                           	         	 +$185,000

Construction Administration                                 				 +$167,000

Construction budget available:							$2,752,000

Gate operation automation still needs to be designed and bid while dam rehab is on-going.

The estimate for design and construction of the gate automation is $253,000.

Three bids were opened and reviewed on June 24, 2016, they all came in significantly over budget with the following results:

Low bid complete price (base bid + Alt 1+ allowances)				$3,475,181

Construction Contingency								 +$185,000

Construction Administration							 +$167,000

Gate operation automation						 		 +$253,000

Total Estimated Construction Cost						$4,080,181

Construction budget	 available						          -$2,752,000

Project shortfall for construction						          -$1,328,181

It is estimated that the project would require an additional $1.3M+ to be completed with automated gates, fish passage and all required repairs. Unknown conditions discovered after construction commences will likely increase costs above those currently estimated. Operation costs are estimated to exceed $160,000 per year to safely maintain and operate the dam. Removal of the dam is estimated to cost $1,674,000+/-. Most of that amount could be provided by the previously authorized WDNR grant funding.

The project budget includes $400,000 from a WDNR Municipal Dam Grant and $980,716.5 from a WDNR Stewardship Grant.  The County’s match money for the grants includes $1M+ spent on the EPA Milwaukee River Sediment Cleanup project.  Although used as a grant match, that funding is not available to spend on the Estabrook Dam Rehab project and is not included in the budget.

# Recommendation

The DPRC recommends that it be authorized and directed to remove the Estabrook Dam in compliance with the WDNR Operational Order due to the fact that the amount of funding previously identified is insufficient to award a contract for rehabilitation of the dam and conversely, sufficient funding is available for removal of the dam.

Prepared by: Kevin Haley, Landscape Architect, DPRC

Approved by:

| John Dargle, Jr., CPRP, Director |  |  |
| --- | --- | --- |

copy:	County Executive Chris Abele

Raisa Koltun, Chief of Staff, County Executive’s Office

Chairman Theodore Lipscomb, Sr., County Board

Kelly Bablitch, Chief of Staff, County Board

Sup. Marcella Nicholson, Vice-Chair, Parks, Energy & Environment Committee

Jeremy Lucas, Fiscal Mgt. Analyst, Admin & Fiscal Affairs/DAS

Allyson Smith, Parks, Energy & Environment Committee Clerk

Jessica Janz-McKnight, Research and Policy Analyst, Office of the Comptroller

Jeremy Theis, DAS, Facilities Management Director