MCCCSB 2018 Workplan:

Written based on input from board members, staff, consumers and community partners.

PRIORITY #1: Define CCSB Role and Responsibilities under current DHHS structure

- Write a statement

  - WORKING DRAFT AVAILABLE:  Yes

  - WHO: Board, Staff, Consultant

  - MONTH:  MAY

  - Contract Hours Needed: 2-4

  - APPROVAL: CCSB takes action to approve

- Create talking points to explain CCSB to county board, community

  - WORKING DRAFT AVAILABLE: Yes

  - WHO; Board, Staff, Consultant, input from partners

  - MONTH: JULY

  - Contract Hours Needed: 5

  - APROVAL: CCSB takes action to approve

  - TBD- 2019- how does the statement get shared: written materials? website? social media?  Budget?

PRIORITY #2: Describe current picture of comprehensive community based service

system-  who, what, where, how, when, why

- Carry Forward Report

  - WORKING DRAFT AVAILABLE: Yes

  - Board, Staff, Consumers, Consultant

  - MONTH: MAY-JULY

  - Contract Hours Needed: 10

  - APPROVAL: CCSB Takes action to approve

- Distribute Carry Forwaryd report

  - PLAN AVAILABLE: No

  - Staff- TBD

  - Month: JUNE-JULY

  - Contract Hours Needed:  TBD

  - Materials Cost: TBD- Budget Impact

  - CCSB approves distribution plan and list

- 2019- TBD- How does this fit into budget process- can it be used? decision-making? legislation? City/County providers?

PRIORITY #3: Create more advocates AND ENGAGE THE COMMUNITY

- Meet with county board supervisors and administrators

  - Staff prepares plan: HOW TO TALK TO THEM, who, what, where, when,

  - MONTH: SEPTEMBER-OCTOBER?

  - Contract Hours Needed: 5-10?  TBD

  - CCSB approves plan; Staff coordinates communication

PRIORITY #4: STUDY THE FUNDING TRENDS AND COUNTY BUDGET PROCESS

- LEARN HOW TO PARTICIPATE, MAKE RECOMMENDATIONS, BE STRATEGIC

  - Staff presents information

  - MONTH: MAY

  - Contract Hours Needed: 3

  - CCSB approves plan to participate, staff coordinates process

2. REVIEW COUNTY 2019 BUDGET- NOVEMBER

2. Receive POS Contracts- NOVEMBER

PRIORITY #5: MATCH ACTION PLANS TO AVAILABLE MCCCSB RESOURCES

- Propose work plan and resources needed to accomplish

  - Chair and Administrator review, discuss with board

  - MONTH: JULY

  - Contract Hours Needed: TBD

  - CCSB reviews options, modifies plan if needed, approves

- TBD: HOW LONG WILL IT TAKE AT THIS LEVEL OF FUNDING?  SIZE OF BOARD?  Unknown changes in departments? legislation? policy?

Issues to follow: **

1. Birth to Three

2. Transitional Employment

3. TRANSPORTATION

4. STIGMA

5. SHORTAGE OF CANDIDATES FOR DIRECT SERVICE POSITIONS

** A PLAN FOR ADDRESSING EACH OF THESE ISSUES WOULD BE NEEDED TO MOVE FORWARD.